## Instructions
05 — MID Server Configuration
Event Management Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Documents the MID Server installation, configuration, and connector setup that enables on-premises monitoring tools to send events to ServiceNow. The MID Server is the on-premises bridge between customer-side monitoring tools and the ServiceNow cloud instance.
Who fills this out | ECS Solution Architect with customer infrastructure team. MID Server sizing and network configuration require the customer's infrastructure and networking teams.
Sprint window | Sprint 0, Week 1
Estimated effort | 4–8 hours including installation, validation, and connector configuration
Related workbooks | 01 Event Sources
Success criteria
• | MID Server is installed, registered, and validated (green status in ServiceNow).
• | All required firewall ports are open and confirmed by the customer networking team.
• | Each monitoring tool connector is configured and has successfully sent at least one test event.
• | MID Server sizing is confirmed as adequate for peak event volume.
• | MID Server HA configuration is in place if required by event volume or SLA.

## Process Decisions
05 — MID Server Configuration — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Where will the MID Server be hosted — on-premises server or cloud VM? | On-premises server in the customer's data center, close to the monitoring tools. If the customer runs monitoring tools in a cloud VPC, the MID Server can be a cloud VM in the same VPC. |  | Network latency between the MID Server and the monitoring tools directly affects event timeliness. Host the MID Server as close to the monitoring tools as possible.
2 | How many MID Servers are needed? | One MID Server for < 5,000 events/minute. Two or more (clustered) for higher volumes or HA requirements. |  | A single MID Server is the correct starting point for most customers. Add a second for redundancy only if the SLA for event processing is critical.
3 | What OS and Java version? | OOTB supported: Windows Server 2016/2019/2022 or RHEL 7/8/9 / Ubuntu 20.04+. Java: OpenJDK 11 (bundled with MID Server installer — do not use a separate JDK). |  | Using a non-bundled JDK is the most common MID Server installation mistake. Always use the JDK bundled with the ServiceNow MID Server installer.
4 | Will the MID Server be managed by the customer or ECS? | Customer infrastructure team manages the host OS; ECS configures the MID Server application and connectors. Patching cadence must be agreed: ServiceNow MID Server upgrades are released with every platform upgrade. |  | MID Server version must match the ServiceNow instance version. If the customer upgrades the instance without upgrading the MID Server, connectors stop working. Set up the auto-upgrade setting in the MID Server configuration.

## Dependencies
05 — MID Server Configuration — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Server hardware/VM provisioned for MID Server | Pending | Customer | Sprint 0, Wk 1 | Minimum spec: 4 vCPU / 8 GB RAM / 50 GB disk for standard deployments
2 | Firewall rules opened: MID Server → ServiceNow (443/HTTPS outbound) | Pending | Customer | Sprint 0, Wk 1 | MID Server initiates outbound connection to ServiceNow; no inbound rules required from ServiceNow
3 | Firewall rules opened: Monitoring tools → MID Server (tool-specific ports) | Pending | Customer | Sprint 0, Wk 1 | ECS to provide port list per monitoring tool connector
4 | ServiceNow MID Server user account created with mid_server role | Pending | ECS | Sprint 0, Wk 1 | Required for MID Server registration; dedicated account per MID Server
5 | MID Server installer downloaded from ServiceNow instance | Pending | ECS | Sprint 0, Wk 1 | Download from ServiceNow > MID Server > Downloads; version must match instance version

## Configuration Data
05 — MID Server Configuration — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. MID Server Installation
Host OS | Customer to confirm | Windows Server 2019/2022 recommended; RHEL 8/9 also supported
Java version | Bundled OpenJDK 11 (included with installer) | Do NOT install a separate JDK; always use the bundled version
MID Server service account (OS level) | svc_midserver (local or domain) | Minimal OS permissions: read/write to MID Server install directory only
MID Server ServiceNow account | svc_mid_[environment] with mid_server role | One account per MID Server; do not share credentials across MID Servers
Auto-upgrade enabled | Yes | Ensures MID Server version stays in sync with ServiceNow upgrades automatically
Install directory | C:\ServiceNow\MID (Windows) or /opt/servicenow/mid (Linux) | Consistent naming for all MID Servers in the environment
2. Network Configuration
MID Server → ServiceNow (outbound) | TCP 443 (HTTPS) | MID Server initiates; no inbound connection from ServiceNow required
Monitoring tool → MID Server (inbound) | Tool-specific; see connector documentation | Customer networking team to open per the port list ECS provides
MID Server → Monitoring tool (outbound polling, if applicable) | Tool-specific; JDBC tools require outbound from MID Server | Required only for polling-based connectors (JDBC, SNMP); push-based connectors do not require this
Proxy server required? | Customer to confirm | If MID Server reaches ServiceNow via proxy, configure proxy settings in config.xml
3. Connector Configuration
Dynatrace connector | OOTB Dynatrace connector (ServiceNow Store) | Configure in MID Server > Extensions; requires Dynatrace API token
SolarWinds connector | OOTB SolarWinds connector (ServiceNow Store) | Requires SolarWinds Orion REST API enabled and a read-only API credential
Nagios / Icinga connector | JDBC polling or Nagios Event Broker plugin | Confirm connector type based on Nagios version; Icinga 2 supports REST push
Custom connector | MID Server scripted connector (EventSource application) | ECS builds using the OOTB EventSource framework; documented in Consultant Guide tab

## R&R
05 — MID Server Configuration — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Server/VM provisioning for MID Server | I | R | Customer infrastructure team provisions; ECS provides minimum spec
Firewall rule implementation | I | R | Customer networking team executes; ECS provides port specifications
MID Server installation and registration | R | I | ECS installs and registers; customer infrastructure team validates OS-level access
ServiceNow MID Server user account creation | R | I | ECS creates the ServiceNow account; customer IT security to approve
Monitoring tool connector configuration | R | C | ECS configures each connector; customer monitoring team validates data flow
MID Server validation (green status + test event) | R | C | ECS validates; customer confirms test events appear in em_event table
Auto-upgrade configuration | R | I | ECS configures; customer infrastructure team informed of upgrade behaviour
Ongoing MID Server host OS maintenance (patching, monitoring) | I | R | Customer infrastructure team owns OS-level maintenance; ECS owns the MID Server application

## Consultant Guide
05 — MID Server Configuration — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
MID Server Is Sprint 0 Day 1
Nothing in Event Management works without the MID Server being up, registered, and green. Treat it as the first task in Sprint 0, before event rules, before alert configuration, before anything. If the customer's networking or infrastructure team is slow, this becomes the critical path blocker for the entire Event Management workstream.
The Bundled JDK Rule
It sounds like a trivial implementation detail, but customers who install their own JDK instead of the bundled one account for a disproportionate share of MID Server issues. The bundled JDK is tested by ServiceNow against the platform version. Separately installed JDKs drift in patch version and create intermittent TLS and SSL handshake failures that are hard to diagnose. Enforce this rule at installation time.
Auto-Upgrade Is Not Optional
The MID Server must stay in sync with the ServiceNow instance version. If auto-upgrade is disabled and the customer upgrades the instance, the MID Server stops processing events silently — no error in the UI, just an empty em_event table. Turn on auto-upgrade and verify it is working before go-live.
Connector Validation Protocol
After configuring each connector: (1) send a test event from the monitoring tool (most tools have a 'send test alert' button); (2) immediately check Event Management > Events in ServiceNow; (3) the test event should appear within 60 seconds. If it does not appear, check: MID Server status (green?), firewall rules (is the port open?), connector credentials (are they valid?), em_event source field (does it match the expected source name?). Do not proceed to event rules until all connectors are validated.

## Adoption vs Re-engineering
05 — MID Server Configuration — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'Can we skip the MID Server and send events directly from monitoring tools via REST?' | Yes for cloud-native tools that can reach the ServiceNow instance directly (direct REST to the em_event endpoint). No for on-premises monitoring tools that cannot reach ServiceNow directly. | Direct REST is valid for cloud-to-cloud. On-premises tools behind a firewall cannot typically reach ServiceNow directly — the MID Server bridges the gap. | 'If the tool can reach ServiceNow directly, absolutely — we will configure direct REST and skip the MID Server for that source. Let us check the network topology for each tool and use the right connector for each one.' | Yes, for cloud-native sources with direct internet access to ServiceNow. Document which sources use direct REST vs. MID Server.
'We want to install the MID Server on the same server as the monitoring tool.' | Avoid collocating the MID Server with the monitoring tool. The MID Server is a JVM process that competes for CPU and memory, which can impact monitoring tool performance during event storms. | During a network storm or major outage, the monitoring tool generates maximum event volume at exactly the same time as the MID Server is most stressed. Collocated deployments fail at the worst possible moment. | 'We strongly recommend a dedicated host — even a small VM. The MID Server and the monitoring tool both spike under load at the same time, which is when you least want resource contention.' | Only if a dedicated host is genuinely impossible. Document the risk and add MID Server host resource monitoring to the monitoring tool's own alert scope.

## ServiceNow Mapping
05 — MID Server Configuration — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. MID Server Tables
MID Server table | ecc_agent | Registry of registered MID Servers and their status
MID Server parameter table | ecc_agent_ext | Configuration parameters per MID Server (proxy, auto-upgrade, etc.)
MID Server queue (inbound) | ecc_queue (queue = input) | Events from monitoring tools arrive here before processing
MID Server queue (outbound) | ecc_queue (queue = output) | Commands sent from ServiceNow to MID Server
2. Key MID Server Configuration Files
config.xml | Primary MID Server configuration file | Contains ServiceNow instance URL, credentials, proxy settings, and extension configurations
wrapper.conf | JVM heap settings | Default heap: -Xmx512m; increase to -Xmx2048m for high-volume deployments
extensions/ directory | Connector extension files | Monitoring tool connectors installed as extension JARs or scripts in this directory
3. OOTB Features Used
MID Server Extensions | Monitoring tool connectors | Installed from ServiceNow Store or MID Server Extensions module
MID Server Cluster | HA configuration for high-volume deployments | Configured via MID Server cluster properties; load balances event processing across nodes
Auto-Upgrade | Keeps MID Server version in sync with instance | Configured via ecc_agent_ext parameter 'mid.auto_upgrade.enabled'