## Instructions
06 — Operator Workspace Setup
Event Management Foundations Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Event Management Operator Workspace configuration — alert views, ownership assignment, notification rules, and the daily operational workflow for the team who will manage alerts post-go-live.
Who fills this out | ECS Solution Architect with the Service Desk Manager and designated Event Management operators. Workspace configuration must be validated by the actual operators, not only by management.
Sprint window | Sprint 1, Week 2 — Sprint 2, Week 1 (validated in UAT)
Estimated effort | 4–6 hours including workspace configuration, view design, and operator walkthrough
Related workbooks | 03 Alert Promotion Rules · 04 CI Correlation Mapping
Success criteria
• | Operator Workspace is accessible to all designated operators with the correct role assignment.
• | Alert views are configured with the agreed filter sets (by priority, by assignment group, by service).
• | Alert ownership and escalation workflow is defined and documented.
• | Notification rules (alert created, alert severity changed, alert promoted) are configured and tested.
• | Operators have completed a 60-minute walkthrough of the workspace before go-live.
• | A daily operational runbook is produced from this workbook for the operators to reference.

## Process Decisions
06 — Operator Workspace Setup — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Who are the designated Event Management operators at go-live? | Identify by name. Minimum: one primary operator per shift (or on-call rotation) and a named backup. Do not rely on a generic 'monitoring team' — unnamed operators are no operators. |  | The most common Event Management go-live failure is having the workspace configured correctly but no one accountable for watching it. Name the operators before go-live, not after.
2 | What alert views are needed? | Three OOTB views at minimum: (1) All Open Alerts (by severity); (2) My Assignment Group Alerts; (3) Unacknowledged Critical/Major Alerts. Add service-level views if Business Service maps are in scope. |  | Avoid creating more than 5–6 views at MVP — operators who cannot decide which view to use default to none of them.
3 | What is the alert acknowledgement SLA? | Critical (Severity 1): acknowledge within 5 minutes. Major (Severity 2): acknowledge within 15 minutes. Minor (Severity 3): acknowledge within 60 minutes. |  | Acknowledgement SLA drives the flapping/escalation thresholds in workbook 02. The values must be consistent across both workbooks.
4 | How will operators be notified of new Critical/Major alerts outside business hours? | Use OOTB Event Management notification rules to send email and/or SMS on Severity 1/2 alert creation. Integrate with on-call roster (PagerDuty, OpsGenie, or ServiceNow On-Call) if available. |  | Email alone is insufficient for out-of-hours critical alerts. Confirm the on-call notification mechanism before go-live.
5 | Will operators use the OOTB Event Management Workspace or the classic Alerts list? | OOTB Event Management Workspace (Event Management > Workspace). The classic Alerts list view is retained for administrative purposes but operators should work from the Workspace. |  | The Workspace provides the operator-centric view with grouped alerts, CI context, and one-click incident promotion. The classic list view is for configuration and reporting, not for daily operations.

## Dependencies
06 — Operator Workspace Setup — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Alert promotion rules configured (workbook 03) | Pending | ECS | Sprint 1, Wk 1 | Workspace shows promoted incidents alongside alerts; requires promotion to be working
2 | Operator user accounts created with evt_mgmt_operator role | Pending | ECS + Customer | Sprint 1, Wk 2 | Operators need evt_mgmt_operator role; Service Desk Manager needs evt_mgmt_admin
3 | On-call roster / notification integration confirmed (PagerDuty, OpsGenie, etc.) | Pending | Customer | Sprint 1, Wk 2 | Required for out-of-hours critical alert notifications; customer to confirm tooling
4 | Alert views agreed with designated operators | Pending | ECS + Customer | Sprint 1, Wk 2 | Views must be designed with the actual operators, not only management

## Configuration Data
06 — Operator Workspace Setup — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Role Assignment
Event Management operator role | evt_mgmt_operator | All designated operators receive this role; grants access to Workspace and alert acknowledgement
Event Management admin role | evt_mgmt_admin | Service Desk Manager and ECS; grants access to rule configuration and workspace administration
Event Management integration role | evt_mgmt_integration | Monitoring tool service accounts only; no human users should have this role
Designated operators at go-live | Customer to name | List all named operators before go-live; unnamed = no coverage
2. Alert Views
View 1 — All Open Alerts (by severity) | Filter: state = Open, sorted by severity ASC, then created DESC | Default view; shows the most critical unresolved alerts first
View 2 — My Assignment Group | Filter: assignment_group IN (current user's groups), state = Open | Operator-specific view; each operator sees only their team's alerts
View 3 — Unacknowledged Critical/Major | Filter: severity IN (1,2), acknowledged = false, state = Open | Escalation view; used by the Service Desk Manager to identify missed critical alerts
View 4 — Service-Level (Phase 2) | Filter: business_service = [service name] | Deferred until Business Service maps are built in Phase 2
3. Notification Rules
Critical alert created | Email + on-call notification to primary operator and backup within 60 seconds of alert creation | Severity 1 only; immediate notification regardless of time of day
Major alert created (business hours) | Email to assignment group within 2 minutes of alert creation | Severity 2 during business hours; on-call notification outside business hours
Alert unacknowledged at SLA breach | Escalation email to Service Desk Manager + on-call backup | Drives escalation without manual monitoring of the workspace
Alert auto-resolved | Work note on linked incident + email to incident assignee | Closes the loop for the incident team; confirms the monitoring tool sent a recovery signal
On-call integration (if applicable) | Customer to confirm: PagerDuty, OpsGenie, or ServiceNow On-Call | ECS configures the integration based on customer's on-call tooling
4. Acknowledgement SLA
Severity 1 (Critical) acknowledgement window | 5 minutes | Triggers escalation notification if not acknowledged within 5 minutes
Severity 2 (Major) acknowledgement window | 15 minutes | Consistent with Incident SLA Priority 2 response time
Severity 3 (Minor) acknowledgement window | 60 minutes | Lower urgency; operators review at next check-in

## R&R
06 — Operator Workspace Setup — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Operator identification and role assignment | I | R | Customer Service Desk Manager names operators; ECS assigns roles in ServiceNow
Alert view design (agreed with operators) | R | C | ECS designs initial views; operators validate and request adjustments
Notification rule configuration | R | C | ECS configures; customer confirms notification recipients and on-call integration
On-call integration setup (PagerDuty, OpsGenie, etc.) | C | R | Customer owns on-call tooling; ECS provides the ServiceNow webhook configuration
Acknowledgement SLA definition | C | R | Customer Service Desk Manager defines SLA targets; ECS configures the escalation rules
Operator walkthrough and workspace training | R | I | ECS leads the 60-minute walkthrough; all designated operators must attend
Post-go-live workspace optimisation (30-day review) | R | C | ECS reviews view usage and notification noise at 30 days; customer approves adjustments

## Consultant Guide
06 — Operator Workspace Setup — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The Workspace Is Where Adoption Lives or Dies
A technically perfect Event Management implementation fails if operators do not use the workspace. The workspace training session is not optional — it is the moment where the operators either adopt the tool or find workarounds (usually: keep using their old monitoring tool dashboards). Spend time in the workspace with the operators before go-live. Let them configure their own views. Answer the 'why would I use this instead of what I already have?' question honestly.
Alert Fatigue Is the Enemy
The workspace must show operators only what they need to act on. If the default view has 500 open alerts, operators will ignore the workspace. The acknowledgement SLA, the suppression rules (workbook 02), and the promotion thresholds (workbook 03) all contribute to alert fatigue. Run a 2-week pilot with real events before go-live and count: how many alerts are in the operator's view at any given time? Target < 20 open, unacknowledged alerts in the primary view at any given time during normal operations.
Named Operators Before Go-Live
This seems obvious but frequently gets deferred. 'The monitoring team will handle it' is not a named operator. Get the Service Desk Manager to name the primary operator and backup per shift, assign the evt_mgmt_operator role to those individuals, and confirm they have completed the workspace walkthrough. Document this in the Operator Runbook.
Operator Runbook
Produce a 2-page daily operations runbook from this workbook before go-live. Contents: (1) how to log into the Workspace; (2) which view to check first; (3) how to acknowledge an alert; (4) how to manually promote an alert to an incident; (5) how to handle an alert storm; (6) who to escalate to if the workspace is down. The runbook lives in the project SharePoint alongside the workbook.

## Adoption vs Re-engineering
06 — Operator Workspace Setup — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We will keep using our monitoring tool dashboards and only use ServiceNow for incidents.' | Use the Event Management Workspace as the primary operational view. Monitoring tool dashboards are still available for tool-specific deep-dive, but the ServiceNow workspace is the single pane of glass for cross-tool operations. | If operators continue to live in the monitoring tool dashboards, the alert acknowledgement and escalation workflow breaks. The workspace provides the cross-tool view that no individual monitoring tool can provide. | 'Your monitoring tool dashboards are excellent for deep-diving into a specific tool's metrics — keep them. The ServiceNow workspace gives you the view across all of your tools together, which is the view you need when something is actually on fire.' | Only if the customer has a single monitoring tool and does not expect to add more. Even then, the workspace provides the incident linkage that the monitoring tool cannot.
'Can we build a custom portal for our operators instead of using the OOTB workspace?' | Use the OOTB Event Management Workspace. It receives ServiceNow product investment with every release. Custom portals become orphaned after the first platform upgrade. | Custom portals require ongoing maintenance as the Event Management data model evolves. The OOTB workspace gains new features (AI-assisted correlation, topology maps, etc.) in every release — custom portals miss all of it. | 'The OOTB workspace has come a long way — let me show you the current version. If there is something specific it cannot do, we can look at whether it is on the roadmap before we decide to build around it.' | Only if there is a documented accessibility requirement the OOTB workspace cannot meet. Even then, consider Service Portal as a lighter alternative to a fully custom portal.

## ServiceNow Mapping
06 — Operator Workspace Setup — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Workspace Tables
Operator workspace configuration | em_workspace_config | Defines workspace layout, available widgets, and default view
Alert view table | em_alert_view | Custom alert filter views accessible from the workspace
Notification rule table | sysevent_email_action (for email) + em_notification_rule | Event Management-specific notification rules; reference via em_alert event triggers
2. Required Roles
evt_mgmt_operator | Alert acknowledgement, manual promotion, workspace access | Assign to all designated Event Management operators
evt_mgmt_admin | Workspace administration, view management, rule access | Assign to Service Desk Manager and ECS during implementation
evt_mgmt_integration | Event ingestion only (monitoring tool service accounts) | No human users; monitoring tool service accounts only
3. OOTB Features Used
Event Management Workspace | Primary operator interface for alert management | Event Management > Workspace; mobile-accessible via the ServiceNow mobile app
Alert Acknowledgement | Marks an alert as being reviewed by an operator | Stops the acknowledgement SLA escalation timer
Manual Incident Promotion | One-click promotion from alert to incident within the Workspace | Available for Severity 3–5 alerts not covered by auto-promotion rules
Workspace Notification Rules | Real-time notifications for alert lifecycle events | Configured via Event Management > Administration > Notification Rules