## Instructions
01 — Service Health Maps
Event Management Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Business Service map configuration that enables service-level alert grouping, service health scoring, and stakeholder-facing health dashboards. Service Health Maps are the bridge between CI-level event noise and business-outcome reporting.
Who fills this out | ECS Solution Architect with customer Service Owners and CMDB team. Service scope and CI membership must be confirmed by the service owner, not ECS alone.
Sprint window | Sprint 3–4 (after CI correlation rate ≥ 85% from AP-08)
Estimated effort | 8–12 hours including service scoping, map build, and health score calibration
Related workbooks | AP-08 Workbook 04 — CI Correlation Mapping · CMDB CSDM Pack · Foundation Data Pack
Success criteria
• | Top 10 business services have confirmed CI membership and a named service owner.
• | Service Health Score thresholds (Operational / Degraded / Critical) are agreed and configured.
• | Service health dashboard is accessible to service owners with no custom development.
• | Alert grouping by business service is working: related CI alerts roll up to the service-level parent.
• | At least one end-to-end service impact scenario is tested (CI alert → service health change → stakeholder notification).

## Process Decisions
01 — Service Health Maps — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which business services are in scope for Phase 1 health maps? | Start with the 5–10 services that are most sensitive to IT events — typically services that are covered by SLAs, have executive sponsors, or have the highest incident volume. Build maps for others in Phase 2. |  | Mapping every service at once overwhelms the workshop and produces low-quality maps. The first 5–10 maps, done well, build the template for everything that follows.
2 | What is the health scoring model — availability only, or a composite score? | OOTB Service Health uses a composite model: critical CIs degrade health more than non-critical CIs, and the number of degraded CIs relative to total CI count drives the health percentage. Accept the OOTB model at MVP. |  | Custom health scoring algorithms are rarely needed and create upgrade risk. The OOTB model is transparent, configurable, and defensible to stakeholders.
3 | Should service health trigger notifications to business stakeholders? | Yes — configure OOTB service health notifications to the service owner email when health drops below the Degraded threshold. Do not notify on every CI alert, only on service health state changes. |  | Notifying stakeholders on every CI alert trains them to ignore notifications. Notify on service health state change only — this is the signal that matters to the business.
4 | How will dynamic CIs (cloud VMs, containers) affect service health accuracy? | Use Discovery / cloud connector to keep CI membership current. Flag dynamic services explicitly — health scores for services with high CI churn are less reliable until Discovery is mature. |  | A service map that references deleted or spun-up CIs not yet in the CMDB produces misleading health scores. Coordinate with the Discovery workstream before enabling health maps for cloud-heavy services.
5 | Will service maps be manually maintained or Discovery-derived? | Manual maps for the first 5–10 services at MVP (fastest to deliver). Discovery-derived maps for Phase 2 once Discovery is tuned to the service topology. |  | Discovery-derived maps are more accurate and self-maintaining but require a mature Discovery implementation. Manual maps are the right MVP trade-off.
6 | What is the health score threshold for Degraded and Critical states? | Degraded: health score < 80%. Critical: health score < 50%. These are OOTB defaults and work well for most customers at MVP. Calibrate after 30 days of production data. |  | The right thresholds depend on service criticality and CI count. A service with 2 CIs where 1 fails hits 50% immediately; a service with 20 CIs where 2 fail is at 90%. Confirm thresholds per service, not globally.

## Dependencies
01 — Service Health Maps — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | CI correlation rate ≥ 85% (AP-08, Workbook 04) | Pending | ECS | Before Sprint 3 | Service maps are only meaningful if the CI correlation is reliable
2 | Business services identified and named in CMDB (cmdb_ci_service) | Pending | Customer + ECS | Sprint 2, Wk 2 | Service map build requires CI service records to exist in the CMDB
3 | CI membership list per service confirmed by service owner | Pending | Customer | Sprint 3, Wk 1 | Service owner must approve CI scope — do not build maps without this sign-off
4 | OOTB Service Mapping plugin activated (com.sn_sm) | Pending | ECS | Sprint 2, Wk 2 | Service Mapping plugin is required for automated topology discovery in Phase 2
5 | Alert grouping by service tested and validated (AP-08, Workbook 02) | Pending | ECS | Sprint 2 | Correlation rules from AP-08 must be working before service-level grouping is testable

## Configuration Data
01 — Service Health Maps — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Business Service Registry
Service 1 — name and owner | TBD | Customer Service Owner to confirm
Service 2 — name and owner | TBD | Customer Service Owner to confirm
Service 3 — name and owner | TBD | Customer Service Owner to confirm
Service 4 — name and owner | TBD | Customer Service Owner to confirm
Service 5 — name and owner | TBD | Customer Service Owner to confirm
Additional services (Phase 2) | TBD | Defer to Phase 2 after MVP maps are validated
2. Health Score Configuration
Health score model | OOTB composite model (CI count × CI criticality weight) | Accept OOTB at MVP; custom model requires development and upgrade testing
Degraded threshold | < 80% health score | Service owner and Service Desk Manager to confirm; adjust per service if needed
Critical threshold | < 50% health score | Service owner and Service Desk Manager to confirm; triggers stakeholder notification
CI criticality weighting | OOTB: critical CIs weighted 2× non-critical | Requires CI criticality attribute to be populated on in-scope CIs
Health score refresh interval | Every 5 minutes (OOTB default) | Accept OOTB; reducing interval increases system load
3. Notification Configuration
Degraded → notification target | Service owner email | Customer to confirm service owner email per service
Critical → notification target | Service owner + IT Manager + on-call operator | Ensure on-call integration is configured (AP-08, Workbook 06)
Notification on health improvement (recovery) | Yes — notify service owner when health returns to Operational | Closes the communication loop for stakeholders
Notification rate limiting | One notification per state change; suppress repeats within 30 minutes | Prevents notification storms during prolonged degradation

## R&R
01 — Service Health Maps — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Business service scope (which services get maps first) | C | R | Customer CIO/IT Manager decides priority; ECS documents and builds
CI membership confirmation per service | I | R | Service owner signs off on which CIs belong to their service
Service map build in CMDB | R | C | ECS builds the map; service owner validates CI coverage
Health score threshold calibration | R | C | ECS configures OOTB thresholds; service owner approves for their service
Stakeholder notification list per service | I | R | Service owner provides the list; ECS configures the notification rule
End-to-end service health scenario testing | R | C | ECS executes test; service owner validates the health dashboard response
Post-go-live health score tuning (30-day review) | R | C | ECS reviews with 30 days of data; service owner approves threshold changes

## Consultant Guide
01 — Service Health Maps — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Service Maps Are About Business Conversations, Not Technology
The service health map build is the moment where IT and the business start speaking the same language. A CI alert means nothing to a service owner; 'your CRM service is at 60% health' means something. Run the service scoping session with the service owner present, not just the CMDB team — the service owner knows what matters to the business, the CMDB team knows what is technically connected. You need both.
The CI Criticality Attribute Problem
The OOTB health score model weights critical CIs more heavily. But most customers have never populated the cmdb_ci.criticality attribute. Before the service map build, run a report: what percentage of in-scope CIs have criticality populated? If it is less than 50%, the weighting model produces misleading results. In that case, configure the health model without criticality weighting until the attribute is populated in Phase 2.
Manual vs Discovery-Derived Maps
Manual maps take 30–60 minutes per service and are immediately accurate — the service owner names the CIs. Discovery-derived maps take days to tune but automatically update when the service topology changes. At MVP, manual maps for the top 5–10 services are the right trade-off. Start the Discovery tuning conversation early so Phase 2 maps can be derived rather than maintained.
The Health Dashboard Is a Stakeholder Management Tool
Show the health dashboard to the IT leadership team before go-live. Not for approval — for socialization. Stakeholders who see the dashboard before a real incident are far less likely to panic when they see a 60% health score during an actual event. The first time should not be during a crisis.

## Adoption vs Re-engineering
01 — Service Health Maps — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We want a custom health scoring algorithm that weights our most critical services differently.' | Use the OOTB CI criticality weighting plus per-service threshold configuration to model service criticality. No custom code required. | Custom scoring algorithms require scripting, survive platform upgrades poorly, and are difficult for customer admins to maintain. | 'The OOTB model gives you two levers: CI criticality weighting and per-service thresholds. Let me show you how those two combined handle the differentiation you are looking for without writing a single line of code.' | Only if the customer's service criticality model genuinely cannot be expressed through CI criticality + threshold tuning. Document the business case before building.
'Can we integrate the health dashboard with our executive reporting portal?' | Use the OOTB Performance Analytics integration for ServiceNow data export. Service health scores are PA indicators and can be exposed via the PA API. | Custom portal integrations require ongoing maintenance as the ServiceNow data model evolves. The PA API is stable and version-controlled. | 'The PA API is the right integration point — health scores are already PA indicators and the API is documented and stable. That is a Phase 2 integration item; let us get the maps right first.' | Yes — PA API export is OOTB and supportable. Scope this as a Phase 2 integration item.

## ServiceNow Mapping
01 — Service Health Maps — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Service Map Tables
Business Service table | cmdb_ci_service | Parent record for each business service; linked to CI members via service_ci relationship
Service CI relationship table | service_ci | Maps CIs to services; drives health score calculation
Service health score table | cmdb_service_health | Stores current and historical health scores per service
Service health notification rule | em_service_health_notification_rule | Drives stakeholder alerts on health state change
2. Key Configuration Points
Service health scoring | Configured via Service Mapping > Service Health | Threshold sliders for Degraded and Critical in the service health configuration
CI criticality weighting | cmdb_ci.criticality attribute (1=Critical, 2=High, 3=Medium, 4=Low) | Must be populated on in-scope CIs for weighting to be meaningful
Service health dashboard | OOTB Service Health dashboard in Event Management Workspace | No custom development; add service widgets from the OOTB widget library
3. OOTB Features Used
Service Mapping plugin (com.sn_sm) | Automated service topology discovery | Required for Discovery-derived maps in Phase 2
Service Health Score | Composite CI-based health calculation | OOTB; no custom development; configured via Service Mapping admin
Service Health Notifications | Stakeholder alerts on health state change | Configured via Event Management notification rules
Performance Analytics — Service Health Indicators | Long-term health trend reporting | Health scores are PA indicators out of the box; enable PA collection for trend reporting