## Instructions
02 — Storm Management
Event Management Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the configuration for detecting, containing, and recovering from event storms — periods of massively elevated event volume triggered by major outages, failed patches, or network events. Storm management is the difference between Event Management surviving a P1 incident and becoming part of the problem.
Who fills this out | ECS Solution Architect. Storm management is primarily an ECS-owned configuration track. Customer IT Ops lead validates storm thresholds against historical incident data.
Sprint window | Sprint 3–4 (after baseline event rules are stable from AP-08)
Estimated effort | 6–8 hours including threshold design, storm simulation, and recovery testing
Related workbooks | AP-08 Workbook 02 — Event Rules Baseline · AP-09 Workbook 01 — Service Health Maps
Success criteria
• | Storm detection rule is configured with agreed thresholds (events/minute per source).
• | Storm parent alert creation is working — a single parent alert represents the storm, not hundreds of individual alerts.
• | Storm suppression is in place: during a storm, low-severity alerts from the storm source are suppressed.
• | Storm notification to the Service Desk Manager is configured and tested.
• | Storm recovery procedure is documented in the Operator Runbook.
• | A storm simulation test has been executed successfully before go-live.

## Process Decisions
02 — Storm Management — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What event volume threshold defines a storm? | ≥ 100 events per minute from a single source within a 5-minute window. This is above the 99th percentile of normal operations for most customers. |  | Setting the threshold too low creates false storm alerts during legitimate high-activity periods (e.g., patching). Setting it too high means a real storm is not detected until the queue is already overwhelmed. 100 events/minute is the right starting point; tune after 30 days of production data.
2 | Should low-severity events be suppressed during a storm? | Yes — suppress Severity 4–5 events from the storm source during the storm window. Severity 1–3 events continue to be processed as alerts. |  | During a storm, Severity 4–5 events are almost always noise caused by the root-cause event propagating. Suppressing them keeps the operator workspace actionable.
3 | How is the storm resolved — automatic or operator-confirmed? | Automatic: when event volume drops below the storm threshold for 10 consecutive minutes, the storm alert closes and suppression ends. Operator receives a recovery notification. |  | Requiring operator confirmation to close a storm alert creates additional toil during an already stressful incident. Automatic closure with a notification is the right balance.
4 | Should storm events from non-production sources be handled differently? | Yes — non-production storms route to the Event Triage group, not the production operator queue. Do not suppress — non-production storms can mask real events if suppressed entirely. |  | Non-production patching and deployment activities regularly generate event storms. Routing them to a separate triage queue keeps the production operator view clean without losing visibility.
5 | What happens to the individual alerts created before the storm was detected? | The storm correlation rule retroactively links alerts created in the storm window to the parent storm alert. Individual alerts are not deleted but are de-emphasized in the operator workspace. |  | Retroactive linkage is the OOTB behaviour. It is more transparent than deleting pre-storm alerts and preserves the audit trail.
6 | What is the storm notification list? | Service Desk Manager + on-call IT Manager. Storm notifications are high-priority and sent via email and on-call system (PagerDuty/OpsGenie if configured). |  | Storm notifications are a management escalation, not an operator task. Notify management so they can communicate to stakeholders and authorize additional resources.

## Dependencies
02 — Storm Management — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Event rules baseline stable and validated in production (AP-08, Workbook 02) | Pending | ECS | Before Sprint 3 | Storm detection builds on top of the baseline event rules; unstable rules produce false storm triggers
2 | Historical event volume data by source (peak events/minute) | Pending | Customer | Sprint 2, Wk 2 | Required to calibrate storm thresholds; use the monitoring tool's own metrics if em_event history is unavailable
3 | On-call notification integration configured (AP-08, Workbook 06) | Pending | ECS | Sprint 2 | Storm notifications route through the on-call system; must be working before storm management is tested
4 | Storm simulation approval from customer IT Manager | Pending | Customer | Sprint 3, Wk 2 | Storm simulation requires generating high event volume in the test environment; customer IT Manager must approve

## Configuration Data
02 — Storm Management — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Storm Detection Thresholds
Storm volume threshold (events/minute) | 100 events/minute from a single source in a 5-minute window | Customer IT Ops lead to validate against historical peak event data
Storm detection window | 5 minutes | OOTB correlation rule window; accept at MVP
Storm recovery window | 10 consecutive minutes below threshold | Automatic closure condition; adjust if storms are naturally intermittent in the customer environment
Non-production storm threshold | Same threshold; route to Event Triage group instead of operator queue | Different routing, same detection logic
2. Storm Correlation Rule
Rule name | EM Storm Detection — [Source Name] | Create one rule per major event source to allow per-source threshold tuning
Parent alert name pattern | EVENT STORM — [Source] — [Timestamp] | Consistent naming makes storm alerts immediately recognizable in the operator workspace
Severity of storm parent alert | Severity 1 (Critical) | Storm parent alert is always Critical regardless of the severity of individual storm alerts
Storm alert assignment group | Event Management Operators (production) or Event Triage (non-production) | Route to the group with authority to coordinate the storm response
3. Suppression Configuration During Storm
Suppress Severity 4–5 events during storm | Yes — suppress from the storm source for the duration of the storm window | Prevents noise from overwhelming the operator workspace while the storm parent alert is active
Continue processing Severity 1–3 events during storm | Yes — all high-severity events continue as individual alerts linked to the storm parent | High-severity events during a storm may have different root causes; do not suppress
Suppression auto-lift on storm recovery | Yes — suppression ends when storm alert closes | Automatic; no operator action required to re-enable suppression after recovery
4. Notification Configuration
Storm detected — notification targets | Service Desk Manager + on-call IT Manager | Customer to confirm names and email/on-call IDs
Storm recovery — notification targets | Same as storm detected list | Recovery notification closes the communication loop
Notification channel | Email + on-call system (PagerDuty/OpsGenie) | Customer to confirm on-call system; ECS configures the ServiceNow-side webhook

## R&R
02 — Storm Management — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Storm threshold calibration | R | C | ECS designs based on historical volume data; IT Ops lead approves
Storm simulation test authorization | I | R | Customer IT Manager must approve; ECS executes the test
Storm simulation execution | R | C | ECS generates synthetic storm events; customer validates workspace behavior
Non-production storm routing decision | C | R | Customer decides triage group staffing; ECS configures routing
Storm notification list confirmation | I | R | Customer Service Desk Manager confirms notification targets
Operator Runbook — storm recovery procedure | R | I | ECS writes the storm recovery procedure; customer operators review and confirm
Post-go-live threshold tuning (30-day review) | R | C | ECS recommends threshold adjustments based on production storm data; customer approves

## Consultant Guide
02 — Storm Management — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Why Storm Management Is a Phase 2 Item
Storm management requires knowing what 'normal' looks like before you can define 'storm.' You cannot calibrate storm thresholds without production event data. AP-08 runs in Sprint 0–1 to establish the event flow; AP-09 storm management runs in Sprint 3–4 after 4–6 weeks of production data. Do not try to configure storm management before the baseline is stable — you will set the wrong thresholds and spend days chasing false positives.
Storm Simulation — Do It Before Go-Live
A storm simulation (generating 100–500 synthetic events per minute in the test environment) is the only way to validate that storm detection, parent alert creation, suppression, and recovery all work correctly under load. Run the simulation in the test environment with the designated operators watching the workspace. This is also the best operator training exercise — there is no substitute for seeing the workspace behavior under a real storm scenario.
The False Positive Problem
If the storm threshold is set too low (e.g., 20 events/minute), legitimate patching windows, deployment pipelines, and batch job completions will trigger false storm alerts. The operators will start ignoring storm notifications within 2 weeks. Always calibrate against historical peak event data and set the threshold at the 99th percentile + 50% headroom. If that data is unavailable, start high and tune down after 30 days.
Per-Source Storm Rules
Create separate storm detection rules per major event source rather than one global rule. Network monitoring tools have different 'normal' volumes than application monitoring tools. A global threshold that is right for the network tool is often wrong for the application tool. Per-source rules allow independent tuning without affecting other sources.

## Adoption vs Re-engineering
02 — Storm Management — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We want to auto-close all alerts during a storm and start fresh after recovery.' | Use the OOTB storm parent alert model: individual alerts are linked to the storm parent but not closed. After the storm, operators review linked alerts and close manually or wait for the monitoring tool's recovery events to auto-close them. | Auto-closing alerts during a storm destroys the audit trail and means that alerts for issues that did not self-resolve (root cause of the storm) are also closed. This is an invisible gap until the next incident review. | 'The storm parent model is designed exactly for this — it de-clutters the operator workspace during the storm without destroying the record of what happened. After the storm, everything is still there for the post-incident review.' | Never auto-close alerts during a storm. The post-incident review depends on that data.
'We want storm suppression to apply to ALL events, not just Severity 4–5.' | Suppress Severity 4–5 only. Severity 1–3 events during a storm continue as individual alerts linked to the storm parent. | Suppressing all events during a storm means that a separate P1 event occurring during the storm window will not create an alert or promote an incident. The storm becomes a window of complete blindness. | 'Suppressing Severity 1–3 during a storm means a different P1 event that starts during the storm is invisible. That is the most dangerous gap we can create. Keep high-severity events flowing — the storm parent keeps the workspace organized.' | Never suppress Severity 1–3 events during a storm.

## ServiceNow Mapping
02 — Storm Management — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Storm Management Tables
Correlation rule table | em_correlation_rule | Storm detection is implemented as an OOTB correlation rule with high-volume conditions
Parent alert table | em_alert (where is_parent = true) | Storm parent alerts are standard em_alert records flagged as parent
Alert-to-parent linkage | em_alert.parent_alert | Links individual storm alerts to the storm parent alert
Suppression rule table | em_event_rule (suppression type) | Storm suppression implemented as event rules activated when storm parent is open
2. OOTB Features Used
Correlation Rule — Storm Detection | High-volume threshold detection per source | Configured via Event Management > Administration > Correlation Rules
Parent Alert Creation | Single parent alert representing the storm | OOTB correlation rule output; no custom development
Alert Suppression During Storm | Low-severity event suppression while storm is active | Event rule with condition on storm parent alert existence
Storm Auto-Recovery | Storm parent closes automatically when volume drops | Configured via the correlation rule recovery condition