## Instructions
03 — AIOps Integration
Event Management Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the configuration for ServiceNow's OOTB AIOps capabilities within Event Management: ML-based noise reduction, anomaly detection, and predictive event correlation. AIOps features are available with the Health Log Analytics and Predictive AIOps licenses and activate automatically once the event data volume is sufficient for ML training.
Who fills this out | ECS Solution Architect (primary). Customer IT Manager confirms license scope and data retention requirements for ML training.
Sprint window | Sprint 4–5 (after ≥ 30 days of production event data)
Estimated effort | 6–10 hours including ML model activation, training validation, and initial results review
Related workbooks | AP-08 Workbook 02 — Event Rules Baseline · AP-09 Workbook 01 — Service Health Maps · AP-09 Workbook 04 — Alert Intelligence
Success criteria
• | AIOps license scope is confirmed and the required plugins are activated.
• | ML training data volume requirement is met (minimum 30 days of clean event data).
• | Anomaly Detection is enabled for at least the top 3 CI classes by event volume.
• | Noise reduction rate is measured: target ≥ 30% reduction in actionable alerts after 60 days.
• | Operators understand ML-generated recommendations and can act on them in the workspace.
• | AIOps performance dashboard is accessible to the Service Desk Manager.

## Process Decisions
03 — AIOps Integration — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Are Health Log Analytics and/or Predictive AIOps licenses in scope? | Confirm with the customer's ServiceNow license agreement. Health Log Analytics drives anomaly detection and noise reduction; Predictive AIOps drives predictive correlation and root cause suggestions. |  | AIOps features require specific licenses that may not be included in the base Event Management license. Confirm before spending time on AIOps configuration.
2 | What is the minimum clean event data volume for ML training? | 30 days of production event data with ≥ 85% CI correlation rate. ML models trained on low-quality or uncorrelated event data produce unreliable results. |  | Starting ML training before the event baseline is clean is the most common AIOps implementation mistake. The model learns the noise as signal and noise reduction goes negative — more alerts, not fewer.
3 | Which CI classes should be prioritized for anomaly detection? | Start with the CI classes that generate the highest event volume and have the cleanest CMDB data: typically servers (cmdb_ci_server), network gear (cmdb_ci_netgear), and databases (cmdb_ci_database). |  | Anomaly detection accuracy improves with event volume per CI class. Starting with high-volume CI classes provides the fastest feedback loop for model quality.
4 | How will operators interact with ML-generated alert recommendations? | OOTB — ML recommendations appear in the Event Management Workspace as 'Suggested Actions' on alerts. Operators can accept or dismiss recommendations. Acceptance feedback improves the model. |  | Operators who understand that their feedback (accept/dismiss) trains the model are more likely to engage with recommendations consistently. Include this in the operator walkthrough.
5 | What noise reduction target is realistic at 60 days? | 30% reduction in actionable alerts at 60 days is a realistic and measurable target for a well-configured implementation. 50%+ is achievable at 90 days with active operator feedback. |  | Promising unrealistic noise reduction numbers (80%+ within 30 days) sets up the implementation for a perception failure. Set conservative targets and exceed them.

## Dependencies
03 — AIOps Integration — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Minimum 30 days of clean production event data with ≥ 85% CI correlation | Pending | ECS | Sprint 4 start | ML model cannot train on low-quality data; this is a hard dependency
2 | Health Log Analytics and/or Predictive AIOps license confirmed | Pending | Customer | Sprint 3, Wk 1 | AIOps features are license-gated; confirm before configuration begins
3 | OOTB AIOps plugins activated (com.snc.health_log_analytics, com.snc.predictive_aiops) | Pending | ECS | Sprint 4, Wk 1 | Plugins must be activated before AIOps configuration is accessible
4 | Operator walkthrough completed and operators trained on ML recommendations | Pending | ECS | Sprint 5, Wk 1 | Operators must understand ML suggestions before go-live; untrained operators ignore or override all recommendations

## Configuration Data
03 — AIOps Integration — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. License and Plugin Scope
Health Log Analytics license | Confirm with customer license team | Drives anomaly detection and ML-based noise reduction
Predictive AIOps license | Confirm with customer license team | Drives predictive correlation and root cause suggestions
Health Log Analytics plugin | com.snc.health_log_analytics | Must be activated before anomaly detection configuration
Predictive AIOps plugin | com.snc.predictive_aiops | Must be activated before predictive correlation configuration
2. ML Training Configuration
Minimum training data period | 30 days of production event data | Do not activate ML features before this threshold is met
Training data CI correlation requirement | ≥ 85% CI correlation rate during training period | Uncorrelated events are noise to the ML model; low correlation = poor model quality
ML model retraining schedule | Weekly automatic retraining (OOTB default) | Accept OOTB; manual retraining available via the AIOps administration interface
Training data scope | All in-scope CI classes from the event sources defined in AP-08, Workbook 01 | Do not limit training data scope unless event volume is extremely high (>1M events/day)
3. Anomaly Detection Configuration
Priority CI class 1 | cmdb_ci_server (servers) | Highest event volume in most environments; best training data for the model
Priority CI class 2 | cmdb_ci_netgear (network) | Second-highest event volume; network events drive a high proportion of P1 incidents
Priority CI class 3 | cmdb_ci_database (databases) | Database events are high-impact; anomaly detection here has the highest business value
Additional CI classes (Phase 2) | Customer to identify based on 30-day event data analysis | Expand anomaly detection after MVP model quality is validated
Anomaly detection sensitivity | Medium (OOTB default) | Accept at MVP; tune after 60 days of feedback from operators
4. AIOps Performance Metrics
Baseline actionable alert count (pre-AIOps) | TBD — measure in the 30-day pre-AIOps period | ECS to report from em_alert data before AIOps activation
Target noise reduction at 60 days | ≥ 30% reduction in actionable alerts | Report via PA indicator; ECS to build the measurement dashboard
Target noise reduction at 90 days | ≥ 50% reduction in actionable alerts | Achievable with active operator feedback loop
Operator recommendation acceptance rate target | ≥ 70% | High acceptance rate indicates model quality and operator trust

## R&R
03 — AIOps Integration — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
License scope confirmation | I | R | Customer IT Manager confirms with ServiceNow account team
AIOps plugin activation | R | I | ECS activates plugins; customer IT Manager approves
ML training period monitoring (data quality) | R | C | ECS monitors CI correlation rate and event volume during training period
Anomaly detection CI class prioritization | R | C | ECS recommends based on event volume data; customer IT Ops lead approves
Operator walkthrough — ML recommendation workflow | R | I | ECS delivers the walkthrough; all designated operators attend
Noise reduction measurement and reporting | R | C | ECS builds the PA measurement dashboard; customer IT Manager reviews monthly
Model sensitivity tuning (60-day review) | R | C | ECS recommends adjustments based on operator feedback data; customer approves

## Consultant Guide
03 — AIOps Integration — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Set Expectations Before You Start
AIOps is the most oversold feature in Event Management. Customer expectations after seeing vendor marketing are often 80%+ noise reduction within 30 days. The realistic trajectory: 0% at day 0 (model training), 10–15% at day 30 (early model), 30% at day 60 (calibrated model), 50%+ at day 90 (operator feedback incorporated). Show customers the maturity curve before activation, not after they are disappointed by early results.
Clean Data Is the Only Variable That Matters
Every AIOps implementation that fails does so because of dirty training data. Uncorrelated events, misconfigured severity mappings, and suppressed events that should have flowed through the model all corrupt the training set. Before activating AIOps, run a 30-day data quality audit: CI correlation rate, severity distribution, event volume per source. If the data is clean, AIOps works. If it is not, AIOps makes things worse.
Operator Feedback Is Not Optional
The ML model improves based on operator accept/dismiss feedback on recommendations. An implementation where operators never interact with recommendations produces a static model that does not improve. Build the feedback expectation into the operator runbook: 'Review and respond to ML suggestions every time you acknowledge an alert. This trains the model.' Include the acceptance rate metric in the weekly management report.
When to Defer AIOps
If the customer's event volume is less than 50,000 events/week, the ML model has insufficient training data to produce reliable results. In this case, defer AIOps to Phase 2 and focus on OOTB correlation rules for noise reduction in Foundations. Do not activate AIOps features for the sake of demonstrating them — a poorly-trained model destroys operator confidence faster than any configuration error.

## Adoption vs Re-engineering
03 — AIOps Integration — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We want AIOps to automatically resolve alerts without operator review.' | Use AIOps for noise reduction recommendations and human-in-the-loop alert promotion decisions. Auto-resolution of alerts should come from monitoring tool recovery events (AP-08, Workbook 03), not from the ML model. | ML models make mistakes, especially in the early training period. Auto-resolving alerts based on ML recommendations without operator review creates invisible gaps where real incidents are suppressed. | 'AIOps makes your operators faster, not optional. The recommendation workflow puts the right information in front of the operator so they can make the right decision in 10 seconds instead of 2 minutes. That is the ROI.' | Only after ≥ 90 days of validated model performance AND operator agreement AND a defined exception process. Document the risk explicitly.
'Can we train the AIOps model on data from our old monitoring system before we go live on ServiceNow?' | No. AIOps trains on em_event and em_alert data from the ServiceNow instance. Historical data from external monitoring systems cannot be imported in a form the model can use. | The ML model requires the full em_event record structure including CMDB correlation, severity mapping, and source attribution. External monitoring data lacks these attributes. | 'The 30-day training period is actually an advantage — it means the model learns your environment as it exists on the new platform, not as it existed in the old system. The old system's patterns may not reflect the new architecture.' | Never. This is an architectural boundary of the ML platform.

## ServiceNow Mapping
03 — AIOps Integration — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. AIOps Tables and Features
Anomaly detection results | ml_anomaly_detection_result | Stores ML-generated anomaly scores per CI per time window
AIOps alert enrichment | em_alert (aiops_* fields) | ML-generated fields appended to em_alert records by the AIOps engine
Operator feedback table | ml_operator_feedback | Stores accept/dismiss feedback from operators; drives model retraining
AIOps administration | Predictive AIOps > Administration | Model management, retraining schedule, sensitivity configuration
2. OOTB AIOps Features in Event Management
Anomaly Detection | CI-level event anomaly scoring | Identifies when a CI's event pattern deviates from its historical baseline
Noise Reduction | ML-based suppression of low-signal events | Reduces actionable alert volume by identifying historically non-actionable events
Predictive Correlation | Cross-source alert grouping based on historical patterns | Groups alerts that have historically co-occurred before a P1 incident
Root Cause Suggestions | ML-suggested probable root cause CI | Surfaces in the operator workspace; improves with operator feedback