## Instructions
04 — Alert Intelligence
Event Management Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the OOTB alert classification, similar alert suggestions, and alert enrichment configuration that makes the operator workspace intelligent rather than just a list of alerts. Alert intelligence features reduce mean-time-to-diagnose by surfacing relevant context alongside each alert without requiring operator research.
Who fills this out | ECS Solution Architect. Customer IT Ops lead validates that suggested similar alerts and enrichment data match operational reality.
Sprint window | Sprint 3–4
Estimated effort | 4–6 hours including enrichment configuration, similar alert testing, and workspace validation
Related workbooks | AP-08 Workbook 02 — Event Rules Baseline · AP-09 Workbook 03 — AIOps Integration
Success criteria
• | Alert enrichment fields (affected service, CI owner, recent changes) are populated on all Severity 1–3 alerts.
• | Similar alert suggestions are surfaced in the workspace for at least 70% of alert types.
• | Alert classification (category/subcategory) is automatically derived from CI class and event type.
• | Related incident history is accessible from the alert without navigating away from the workspace.
• | Alert enrichment does not degrade workspace performance (load time < 3 seconds for the alert detail view).

## Process Decisions
04 — Alert Intelligence — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What contextual information should be displayed on an alert in the workspace? | OOTB: affected CI, CI owner, assigned support group, affected business service, recent changes to the CI (last 72 hours from Change Management), open incidents for the CI, and similar historical alerts. Accept the OOTB default; add custom fields in Phase 2 if needed. |  | Enrichment data must be available without operator navigation. If the operator needs to open 3 separate records to gather context, the workspace is not faster than the old way of working.
2 | Should recent change data be shown on alerts to help diagnose change-induced incidents? | Yes — show the last 5 approved changes to the affected CI in the last 72 hours. This is OOTB via the Change Management integration in the Event Management Workspace. |  | Change-induced incidents account for a significant percentage of P1 events. Surfacing recent changes on the alert reduces mean-time-to-diagnose for this category from hours to seconds.
3 | How will similar alert suggestions be generated — rule-based or ML-based? | Rule-based at MVP (OOTB: alerts from the same source with the same event type and CI class are similar). ML-based similarity activates automatically once AIOps training data is sufficient (see Workbook 03). |  | Rule-based similar alerts work immediately with no training period. ML-based similarity is more accurate but requires 30+ days of data. Start with rule-based and transition to ML-based naturally as the AIOps model matures.
4 | Should alert classification (category/subcategory) be auto-populated? | Yes — derive category from CI class (cmdb_ci.sys_class_name) and subcategory from alert event type. This ensures consistent classification and accurate reporting without manual operator input. |  | Manual alert classification by operators is inconsistent and low-quality. Operators under time pressure skip classification fields. Auto-classification is the only way to get clean category data at scale.

## Dependencies
04 — Alert Intelligence — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | CI class mapping to incident category/subcategory agreed (from ITSM workstream) | Pending | Customer | Sprint 2, Wk 2 | Alert auto-classification must align with the Incident category taxonomy
2 | Change Management integration confirmed working (CHG → Event alert context) | Pending | ECS | Sprint 3, Wk 1 | Recent changes appear on the alert only if the CHG integration is configured
3 | Alert correlation rate ≥ 85% (AP-08, Workbook 04) | Pending | ECS | Before Sprint 3 | Similar alert suggestions require alerts to be correlated to CIs; uncorrelated alerts have no similar alert context

## Configuration Data
04 — Alert Intelligence — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Alert Enrichment Fields
Affected CI — name, class, environment | Auto-populated from em_alert.cmdb_ci | Requires CI correlation to be working
CI owner (support group) | Auto-populated from cmdb_ci.support_group | Requires support_group to be populated on all in-scope CIs
Affected business service | Auto-populated from service_ci relationship | Requires service maps to be built (AP-09, Workbook 01)
Recent changes to CI (last 72 hours) | OOTB Change Management integration — last 5 approved changes | Configured via Event Management > Administration > External Data Sources
Open incidents for CI | Auto-populated from em_alert_task_alert binding | Shows linked incidents and any open incidents for the same CI
2. Alert Classification
Category mapping — cmdb_ci_server | Category: Hardware | ECS to confirm against agreed incident taxonomy
Category mapping — cmdb_ci_netgear | Category: Network | ECS to confirm against agreed incident taxonomy
Category mapping — cmdb_ci_database | Category: Database | ECS to confirm against agreed incident taxonomy
Category mapping — cmdb_ci_application | Category: Software | ECS to confirm against agreed incident taxonomy
Subcategory mapping — event type 'CPU' | Subcategory: Performance | ECS to document full event type to subcategory mapping
Subcategory mapping — event type 'Disk' | Subcategory: Availability | ECS to document full event type to subcategory mapping
Subcategory mapping — event type 'Network' | Subcategory: Connectivity | ECS to document full event type to subcategory mapping
3. Similar Alert Configuration
Rule-based similarity criteria | Same source + same event type + same CI class within 24 hours | OOTB; no configuration required beyond enabling the similar alert widget in the workspace
Similar alert lookback window | 24 hours (OOTB default) | Extend to 72 hours for low-frequency, high-impact alert types if needed
Maximum similar alerts displayed | 10 (OOTB default) | Accept at MVP; operators overwhelmed by too many similar alerts start ignoring them
ML-based similarity (post-AIOps) | Activates automatically when AIOps model is trained | See Workbook 03; ML similarity replaces rule-based when model is ready

## R&R
04 — Alert Intelligence — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Alert enrichment field selection | R | C | ECS selects from OOTB available fields; IT Ops lead validates usefulness
CI class to incident category mapping | R | C | ECS maps based on ITSM taxonomy; customer confirms alignment
Similar alert configuration | R | I | ECS configures; operators validate suggestions match their intuition during UAT
Change Management integration for alert context | R | C | ECS configures the integration; Change Manager confirms change data is appearing correctly
Workspace performance validation (< 3 second load) | R | I | ECS validates; alerts if enrichment queries are degrading performance

## Consultant Guide
04 — Alert Intelligence — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Enrichment vs Performance Trade-Off
Every enrichment field on an alert requires an additional database lookup when the alert is opened. Three to five enrichment fields is the sweet spot — enough context to diagnose without degrading workspace performance. Test workspace alert open time with all enrichment fields active before go-live. If load time exceeds 3 seconds, remove the lowest-value enrichment field, not the highest-value one.
The Change Management Integration ROI
The single highest-value enrichment field is recent changes to the affected CI. Studies across ITSM implementations consistently show that 20–40% of P1 incidents are change-induced. Surfacing recent changes on the alert eliminates the most common time-wasting investigative step (Did someone change something recently?). This field alone reduces MTTR meaningfully and is easy to demonstrate to the IT Manager.
Auto-Classification Is Non-Negotiable
Manual alert classification produces data that is too inconsistent for meaningful reporting. After 90 days of manually classified alerts, the category distribution will reflect which operators were working at the time, not the actual alert mix. Auto-classification from CI class + event type produces consistent data from day one. The data quality compounds over time — at 12 months, the category trends are meaningful for capacity planning and problem management.

## Adoption vs Re-engineering
04 — Alert Intelligence — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We want custom enrichment data from our CMDB that is not in the standard alert view.' | Use the OOTB alert workspace customization to add custom CI attributes to the alert enrichment panel. Most CMDB attributes can be surfaced without custom development. | Custom development for enrichment fields is rarely needed because the OOTB workspace customization supports attribute-level field addition from any related table. | 'Show me which CMDB field you want — most of them can be added through the workspace configuration without writing code. Let us check what is available before we scope a development item.' | Only if the field requires a complex calculation or multi-table join that the workspace field configuration cannot handle.

## ServiceNow Mapping
04 — Alert Intelligence — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Alert Intelligence Tables
Similar alert relationship table | em_alert_similar_alert | Links similar alerts for workspace display
Alert enrichment configuration | em_workspace_config (enrichment section) | Defines which enrichment fields appear in the alert detail panel
Alert classification rules | em_event_rule (classification transform) | Auto-populates category/subcategory on the alert from CI class and event type
2. OOTB Features Used
Alert Enrichment Panel | Contextual data panel in the Event Management Workspace alert detail | Configured via workspace administration; no custom development
Similar Alerts Widget | Shows historically similar alerts alongside the current alert | OOTB workspace widget; enabled in workspace configuration
Recent Changes Widget | Shows last 5 approved changes to the affected CI | Requires Change Management integration; configured via External Data Sources