## Instructions
05 — Remediation Workflows
Event Management Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the auto-remediation and runbook automation configuration that allows ServiceNow to automatically respond to known event patterns without operator intervention. Remediation workflows close the loop from detection to resolution for the most common alert types, reducing MTTR and operator toil.
Who fills this out | ECS Solution Architect with customer IT Ops lead and system administrators. Remediation actions must be approved and tested by the customer's operations team before activation.
Sprint window | Sprint 4–5 (after alert promotion and auto-resolution are stable from AP-08)
Estimated effort | 8–12 hours including runbook design, automation scripting, and approval testing
Related workbooks | AP-08 Workbook 03 — Alert Promotion Rules · AP-09 Workbook 04 — Alert Intelligence
Success criteria
• | Top 5 auto-remediation scenarios are identified, approved, and tested.
• | Runbook Automation (RBA) workflows are configured for each approved scenario.
• | Human-in-the-loop approval step is in place for all destructive remediation actions (restart, failover).
• | Remediation success/failure is logged on the linked incident record.
• | Failed remediation triggers operator notification and escalation.
• | Remediation effectiveness rate (successful auto-remediation / total attempts) is measured and reported.

## Process Decisions
05 — Remediation Workflows — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which alert types are candidates for auto-remediation? | Start with the 5 most common, well-understood, low-risk remediation actions: disk cleanup scripts, service restart, cache flush, connection pool reset, and scheduled job re-trigger. Never auto-remediate actions that could cause data loss or extended downtime without human approval. |  | The right candidates are: high-frequency, well-understood root cause, known remediation that works > 90% of the time, and low blast radius if the remediation fails. Start there.
2 | What approval workflow is required before executing a remediation action? | OOTB: Service Restart and above require a named approver (on-call operator or Service Desk Manager) to confirm via the mobile app or email before the RBA workflow executes. Low-risk actions (cache flush, log rotation) can execute without approval. |  | Never configure auto-remediation without a defined approval tier for each action type. The customer's operations team must own the approval list — ECS cannot approve production remediation actions.
3 | How will remediation success or failure be measured? | Log remediation attempt, action taken, result (success/failure), and duration on the linked incident work note. Failed remediations trigger operator notification and are flagged for post-incident review. |  | Remediation logging is the only way to measure effectiveness and justify the RBA investment. It is also the audit trail that demonstrates due diligence when a remediation fails.
4 | What happens if a remediation action fails? | Notify the on-call operator immediately with the failure detail. Escalate the linked incident to Priority 1 if the remediation failure indicates the issue is worse than initially assessed. |  | Unnoticed remediation failures leave the system in an ambiguous state — the alert closed but the issue was not resolved. The failure notification must be immediate and must go to someone with authority to escalate.
5 | Will MID Server be used for on-premises remediation, or is there a direct API? | MID Server for on-premises actions (Windows restart, Linux service control). Direct REST API for cloud-hosted services that expose a management API. |  | This mirrors the event source decision from AP-08, Workbook 01. The same topology that applies to event sources applies to remediation actions.

## Dependencies
05 — Remediation Workflows — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Alert promotion and auto-resolution working correctly (AP-08, Workbook 03) | Pending | ECS | Before Sprint 4 | Remediation workflows trigger from promoted alerts; unstable promotion = unreliable remediation triggers
2 | Runbook Automation plugin activated (com.snc.runbook_automation) | Pending | ECS | Sprint 4, Wk 1 | RBA workflows require the RBA plugin; activate before remediation design sessions
3 | Customer operations team to approve the remediation candidate list | Pending | Customer IT Ops Lead | Sprint 3, Wk 2 | ECS cannot define which remediation actions are safe to auto-execute; customer operations team must own this list
4 | Test environment with representative CIs available for remediation testing | Pending | Customer | Sprint 4, Wk 1 | All remediation workflows must be tested in the test environment before production activation; customer to confirm test CI availability
5 | MID Server configured (AP-08, Workbook 05) for on-premises remediation | Pending | ECS | Sprint 0 | On-premises remediation requires an active MID Server; same MID Server as event source collection

## Configuration Data
05 — Remediation Workflows — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Approved Remediation Scenarios
Scenario 1 — Disk space cleanup | Action: Run disk cleanup script via MID Server. Approval: None (automated). Scope: Non-production CIs only at MVP. | Safe to automate; low blast radius; high frequency
Scenario 2 — Application service restart | Action: Restart named Windows/Linux service via MID Server. Approval: On-call operator via mobile app. Scope: Non-critical services only. | Requires approval; service restart can cause brief downtime
Scenario 3 — Cache flush | Action: API call to application cache flush endpoint. Approval: None (automated). Scope: Designated caching services only. | Safe to automate; cache flush is stateless and reversible
Scenario 4 — Connection pool reset | Action: API call to application server connection pool reset. Approval: On-call operator. Scope: Database connection pools. | Requires approval; brief connection disruption during reset
Scenario 5 — Scheduled job re-trigger | Action: API call to scheduler to re-trigger failed job. Approval: None (automated). Scope: Idempotent scheduled jobs only. | Safe to automate only for idempotent jobs; customer must confirm idempotency
2. Approval Workflow Configuration
Low-risk actions (no approval) | Cache flush, log rotation, disk cleanup, idempotent job re-trigger | ECS to validate that each no-approval action meets the low-risk criteria
Standard approval actions | Service restart, connection pool reset, process kill | On-call operator approves via ServiceNow mobile app or email within 5 minutes
Elevated approval actions | VM reboot, failover, network config change | On-call operator + Service Desk Manager both must approve; 10-minute window
Approval escalation if no response | Escalate to backup approver; if still no response after 15 min, notify IT Manager and abort remediation | Remediation must not execute if approval window expires; safe default is abort
3. Remediation Logging
Work note on linked incident — attempt | Logged when remediation action is triggered: action name, target CI, timestamp | Automatic via RBA workflow; no manual step required
Work note on linked incident — result | Logged when action completes: success/failure, duration, output (first 500 characters) | Automatic via RBA workflow output step
Remediation failure alert | Notify on-call operator immediately; upgrade incident priority if severity warrants | ECS to configure the failure notification in the RBA workflow
Remediation effectiveness dashboard | PA indicator: successful remediations / total attempts per scenario, weekly | ECS to build the measurement dashboard in Sprint 5

## R&R
05 — Remediation Workflows — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Remediation candidate list approval | I | R | Customer IT Ops Lead defines and approves; ECS documents
Approval tier assignment per action type | R | C | ECS drafts the tier structure; customer IT Manager approves
RBA workflow build | R | I | ECS builds in ServiceNow; customer operations team reviews the workflow logic
Remediation testing in test environment | R | C | ECS executes test scenarios; customer operations team validates results
Production activation approval | I | R | Customer IT Manager signs off on production activation for each scenario
Remediation effectiveness measurement | R | C | ECS builds the PA dashboard; customer IT Manager reviews monthly
Failed remediation post-incident review | R | C | ECS leads the review for failed remediations; customer operations team attends

## Consultant Guide
05 — Remediation Workflows — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Start Small and Build Trust
The fastest path to a failed auto-remediation program is automating too much too soon. Start with the safest, most understood, most reversible actions. Build the operator's trust that the automation works and does not cause harm. After 30 days of successful automated remediations, the operator team will come to ECS asking for more automation — that is the right time to expand scope.
The Approval Workflow Is the Governance Framework
The approval workflow is what makes auto-remediation safe. Every destructive action (restart, reset, reboot) must have a human approval step. The approval step is also a coaching opportunity — the on-call operator who approves a restart learns when it is appropriate and why, which builds institutional knowledge. Design the approval workflow with the customer's ops team, not for them.
Measure Everything
The RBA program justification depends on data. Track: how many remediations were attempted, how many succeeded, how much time was saved per successful remediation (use the MTTR delta), and how many failed and why. Show this data monthly to the IT Manager. A program that resolves 50 incidents per month automatically, each saving 30 minutes of operator time, is easy to defend and easy to expand.
The MID Server Is the Remediation Bridge
On-premises remediation depends on the MID Server being healthy. A MID Server that is under load from event processing will also be slow to execute remediation scripts. If event volume is high and remediation response time is slow, consider a dedicated MID Server for remediation workflows separate from the event source MID Server.

## Adoption vs Re-engineering
05 — Remediation Workflows — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We want to auto-remediate VM reboots without approval.' | VM reboots require explicit operator approval. Place this in the elevated approval tier with dual sign-off. | An auto-rebooted VM that was serving active user sessions causes an outage, not a remediation. The blast radius is too large for zero-approval automation. | 'A VM reboot is a calculated risk — sometimes the right call, sometimes not. The approval step takes 2 minutes and gives the operator the context to make the right decision. That 2 minutes is worth it.' | Never. VM reboots require approval regardless of the customer's confidence level.
'Can we trigger remediation from our monitoring tool directly rather than through ServiceNow?' | Trigger remediation through ServiceNow RBA only. Monitoring tool-triggered remediation bypasses the ITSM record linkage, audit trail, and approval workflow. | Monitoring tool-triggered remediation is invisible to the ITSM system. There is no incident record, no approval audit, no effectiveness measurement. It also creates two parallel remediation programs that quickly become inconsistent. | 'Running remediation through ServiceNow means every action is linked to an incident, approved by the right person, and tracked for effectiveness. Your monitoring tool is great at detecting the issue — ServiceNow is where the response is orchestrated.' | Never. Remediation must flow through the ITSM platform for auditability and governance.

## ServiceNow Mapping
05 — Remediation Workflows — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Runbook Automation Tables
RBA workflow table | rba_workflow | Defines the automated workflow steps, conditions, and approvals
RBA execution history | rba_activity_execution | Logs every RBA execution attempt, outcome, and duration
MID Server command table | ecc_queue (RBA commands) | RBA commands to on-premises systems route through the ecc_queue to the MID Server
2. OOTB Features Used
Runbook Automation (RBA) | ServiceNow's orchestration engine for automated IT actions | Available via the Orchestration license; confirm license scope with customer
MID Server Script Execution | Executes scripts and commands on on-premises systems via MID Server | Uses the PowerShell or SSH activity packs in RBA
REST API Activity | Calls external REST APIs for cloud-hosted service remediation | OOTB REST activity in RBA; no custom development required
Approval Workflow | Human-in-the-loop approval before destructive remediation actions | Standard ServiceNow approval workflow integrated into the RBA execution chain