## Instructions
06 — Advanced Correlation
Event Management Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines multi-source, multi-tier advanced correlation rules that group alerts from different monitoring tools and different CI classes into unified parent alerts representing a single business event. Advanced correlation is the configuration that produces the 'single view of an incident' that operators need to diagnose complex, cross-domain outages.
Who fills this out | ECS Solution Architect. Advanced correlation rules are ECS-owned configuration. Customer IT Ops lead validates that correlation groupings match operational experience.
Sprint window | Sprint 3–4 (after Foundations event rules are stable)
Estimated effort | 8–10 hours including rule design, cross-source testing, and parent alert validation
Related workbooks | AP-08 Workbook 02 — Event Rules Baseline · AP-09 Workbook 01 — Service Health Maps
Success criteria
• | At least 3 multi-source correlation scenarios are configured and tested.
• | Parent alert correctly aggregates child alerts from at least 2 different event sources.
• | Cross-CI-class correlation (e.g., network alert + server alert = related) is working for the top 3 incident patterns.
• | Parent alert severity reflects the highest child alert severity (not an average).
• | Operator workspace correctly shows the parent-child hierarchy without requiring navigation.

## Process Decisions
06 — Advanced Correlation — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What are the most common multi-source incident patterns in this environment? | Interview the IT Ops team: 'When a P1 incident happens, which monitoring tools typically all fire at the same time?' The most common patterns are: network switch failure → server alerts + application alerts from the same segment; database overload → application alerts + end-user experience alerts; storage failure → VM alerts + application alerts. |  | Advanced correlation rules must be built from real incident patterns, not from theoretical alert taxonomy. The IT Ops team holds this knowledge.
2 | What correlation window should be used for multi-source rules? | 10 minutes is the OOTB default and works for most infrastructure-layer incidents. Application-layer incidents (where the root cause takes time to cascade) may need a 20–30 minute window. |  | A correlation window that is too short misses the cascade; too long creates false groupings. Use the customer's historical incident timeline data to calibrate — how long does it typically take for a root cause to produce alerts across all affected tools?
3 | How should parent alert severity be determined? | Parent alert severity = highest severity among child alerts. Do not average. One Severity 1 child in a group makes the parent Severity 1. |  | Averaging severity hides the true impact. A parent alert at Severity 3 (average of 1 and 5) does not promote to an incident. The correct answer is always: if any child is Severity 1, the parent is Severity 1.
4 | Should advanced correlation rules replace or supplement the basic CI-level grouping from AP-08? | Supplement. Advanced correlation rules are additive — they create higher-level parent alerts that group lower-level CI alerts. The CI-level grouping from AP-08 continues to function. |  | Removing CI-level grouping in favour of advanced correlation is risky because advanced rules may miss alerts that do not match the multi-source pattern. Both layers working together produces the best operator experience.

## Dependencies
06 — Advanced Correlation — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | CI-level correlation rules working (AP-08, Workbook 02) | Pending | ECS | Before Sprint 3 | Advanced correlation builds on top of CI-level grouping; must be stable first
2 | Event sources confirmed and validated for all in-scope monitoring tools (AP-08, Workbook 01) | Pending | ECS | Sprint 1 | Cross-source correlation requires all sources to be sending events reliably
3 | IT Ops team historical incident pattern interview completed | Pending | ECS | Sprint 3, Wk 1 | Advanced correlation rules must be designed from real incident patterns; interview is a prerequisite

## Configuration Data
06 — Advanced Correlation — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Multi-Source Correlation Scenarios
Scenario A: Network switch failure cascade | Triggers: SolarWinds network alert (switch) + Dynatrace application alerts (servers in the same segment) within 10 minutes. Parent: 'Network Segment Impact — [Switch CI]'. | Customer to confirm which network segments have the highest P1 exposure
Scenario B: Database overload cascade | Triggers: Database monitoring alert (disk/CPU/connections) + application performance alert (response time degradation) within 20 minutes. Parent: 'Database Impact — [DB CI]'. | 20-minute window to account for application layer cascade lag
Scenario C: Storage failure cascade | Triggers: Storage monitoring alert + VM alerts (same datastore) + application availability alerts within 15 minutes. Parent: 'Storage Impact — [Storage CI]'. | Customer to confirm which datastores host the highest-priority VMs
Additional scenarios (Phase 2) | Customer IT Ops to identify from post-incident reviews | Build additional scenarios from 30-day production incident data analysis
2. Correlation Rule Configuration
Default correlation window | 10 minutes | Adjust per scenario; see individual scenario notes above
Parent alert naming convention | [Pattern Name] — [Root Cause CI] — [Timestamp] | Consistent naming makes parent alerts immediately recognizable
Parent alert severity rule | Severity = MAX(child alert severities) | Never average; highest child severity = parent severity
Maximum child alerts per parent | 50 (OOTB default) | Cap prevents a single parent alert from aggregating an entire storm; storm detection handles high-volume events

## R&R
06 — Advanced Correlation — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Incident pattern interview with IT Ops team | R | C | ECS leads the interview; IT Ops team provides real incident examples
Multi-source correlation scenario design | R | C | ECS designs based on interview findings; IT Ops lead validates
Advanced correlation rule configuration | R | I | ECS configures; customer validates in UAT
Cross-source correlation testing | R | C | ECS generates synthetic multi-source events; IT Ops validates parent alert grouping
Post-go-live rule tuning (30-day review) | R | C | ECS adjusts correlation windows based on production data; customer approves

## Consultant Guide
06 — Advanced Correlation — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The Incident Pattern Interview Is Essential
Do not design advanced correlation rules from theoretical alert taxonomy. Sit with the IT Ops team and ask: 'Walk me through the last three P1 incidents. Which monitoring tools fired? In what order? How long after the root cause did each tool fire?' That conversation produces more useful correlation rule designs than any documentation.
Test With Real Alert Sequences, Not Individual Events
Advanced correlation testing requires generating a sequence of synthetic events from different sources within the correlation window. Send a network alert from SolarWinds, then application alerts from Dynatrace 3 minutes later, then watch the workspace. If the parent alert does not appear, the correlation rule is wrong. This cannot be tested with a single synthetic event.
The Window Calibration Problem
The correlation window must be wide enough to catch the cascade but narrow enough to avoid false groupings. If the window is 30 minutes, two unrelated incidents that happen 25 minutes apart will be incorrectly grouped. Use historical incident timeline data to set the window at 1.5× the observed cascade lag. If cascade lag varies widely, use a narrow window and accept that some correlations will be missed — false positives are worse than missed correlations.

## Adoption vs Re-engineering
06 — Advanced Correlation — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We want one correlation rule that catches every multi-source incident pattern.' | Build separate correlation rules per scenario. One global rule produces false groupings that destroy operator confidence within 2 weeks. | A global correlation rule that catches 'any two alerts from any source within 30 minutes' will group completely unrelated incidents. Every incorrect grouping requires operator time to undo and reduces trust in the system. | 'Separate rules per scenario give you the accuracy to justify the workflow change. A wrong correlation is worse than no correlation — your operators will turn the feature off if it groups unrelated incidents.' | Never. Per-scenario rules are non-negotiable for quality.

## ServiceNow Mapping
06 — Advanced Correlation — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Advanced Correlation Tables
Correlation rule table | em_correlation_rule | Advanced multi-source rules; same table as basic CI-level rules, additional conditions
Parent-child alert linkage | em_alert.parent_alert | All child alerts reference the parent alert sys_id
Correlation event table | em_correlation_event | Logs which events contributed to each correlation rule evaluation
2. OOTB Features Used
Multi-Source Correlation Rules | Cross-source alert grouping based on CI relationship and time window | Configured via Event Management > Administration > Correlation Rules; supports scripted conditions
Parent Alert Hierarchy | Visual parent-child alert grouping in the Operator Workspace | OOTB workspace feature; no custom development