## Instructions
08 — Hypercare and Maturity
Event Management Realization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the 30/60/90-day hypercare activities, tuning checkpoints, and operator maturity framework for Event Management post-go-live. Hypercare is where the Event Management program moves from 'working' to 'optimized.' Without a structured hypercare plan, the program stabilizes at 70% of its potential and the tuning never happens.
Who fills this out | ECS Delivery Manager with Service Desk Manager and IT Manager. Hypercare is a joint accountability between ECS and the customer.
Sprint window | Go-Live + 90 days (Hypercare period)
Estimated effort | 2–4 hours per checkpoint (3 checkpoints = 6–12 hours total ECS effort)
Related workbooks | All AP-08 and AP-09 workbooks · AP-09 Workbook 07 — Analytics and KPIs
Success criteria
• | 30-day checkpoint: all KPIs are measured and compared to targets; top 3 tuning actions identified.
• | 60-day checkpoint: AIOps noise reduction ≥ 30%; correlation rate ≥ 90%; all P1/P2 alerts auto-promoting.
• | 90-day checkpoint: operator maturity assessment completed; Phase 2 scope agreed.
• | Customer operations team can manage and tune Event Management without ECS support for routine operations.
• | Phase 2 scope document is agreed by IT Manager at the 90-day checkpoint.

## Process Decisions
08 — Hypercare and Maturity — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Who owns Event Management operations after go-live? | Designate a named ServiceNow Platform Admin or Event Management Admin who owns day-to-day rule maintenance, operator onboarding, and threshold tuning. This person should have the evt_mgmt_admin role and has completed ECS's operator certification process. |  | Without a named owner, Event Management configurations drift as team members change. The admin designation must happen before go-live, not after the first configuration problem.
2 | What is the criteria for escalating from hypercare to a formal ECS engagement? | Escalate if: CI correlation rate < 75% at 60 days, more than 3 auto-remediation failures per week, more than 5 false storm alerts per week, or operator workspace load time > 5 seconds. |  | Clear escalation criteria prevent both under-escalation (problems that fester) and over-escalation (ECS involvement for issues the customer admin can resolve). These thresholds are the trigger for a formal post-go-live assessment.
3 | What does the Phase 2 scope include? | Standard Phase 2 candidates: Service Mapping for Discovery-derived service maps, AIOps advanced noise reduction, additional remediation scenarios, SIEM integration (Splunk/QRadar), and capacity planning automation. |  | Phase 2 scope is defined at the 90-day checkpoint using actual production data — not speculative requirements from pre-go-live workshops. Production data always reveals the most valuable next investments.

## Dependencies
08 — Hypercare and Maturity — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | All AP-08 and AP-09 workbooks completed and validated in UAT | Pending | ECS | Before Go-Live | Hypercare assumes all Foundations and Realization configurations are in place
2 | Named Event Management Admin designated and trained | Pending | Customer | Go-Live | Admin must be in place before hypercare begins
3 | PA dashboards live and KPI baselines established (Workbook 07) | Pending | ECS | Go-Live | Hypercare checkpoint measurements depend on PA dashboards being operational

## Configuration Data
08 — Hypercare and Maturity — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. 30-Day Hypercare Checkpoint
KPI measurement | Compare CI correlation rate, promotion rate, auto-resolution rate, and alert acknowledgement rate against go-live targets | ECS to pull from PA dashboard; present to Service Desk Manager
Top 3 tuning actions | Identify the 3 highest-impact tuning actions from the first 30 days of production data | Common actions: adjust storm thresholds, fix CI correlation gaps, tune suppression rules
Operator feedback review | Review operator feedback on similar alert suggestions and ML recommendations | High dismiss rates indicate poor model quality or irrelevant suggestions
MID Server health check | Confirm MID Server queue depth < 1,000, no event lag, and auto-upgrade confirmed working | MID Server issues that were manageable in testing often surface at production volume
2. 60-Day Hypercare Checkpoint
AIOps noise reduction measurement | Target: ≥ 30% reduction vs. go-live baseline | If < 30%, review ML training data quality and operator feedback rates
CI correlation rate target | Target: ≥ 90% | Identify and remediate top 20 uncorrelated node values from the Event Triage queue
Advanced correlation validation | Confirm multi-source correlation rules are grouping correctly; review false positive rate | Target: < 10% false positive rate (parent alerts that should not have been grouped)
Operator maturity pulse check | Survey designated operators: 'Is the workspace your primary alert management tool?' Target: 100% yes. | If operators are still using monitoring tool dashboards as primary, the workspace adoption has failed; identify the obstacle
3. 90-Day Checkpoint and Phase 2 Planning
Full KPI review | Compare all 7 core KPIs against targets; identify sustained gaps vs. met targets | Present to IT Manager as the Event Management program report card
Operator maturity assessment | Can the designated admin manage rules, tune thresholds, and onboard new operators without ECS support? | If not, plan an ECS admin coaching session before formal ECS engagement ends
Phase 2 scope agreement | Based on 90 days of production data, agree the Phase 2 scope with IT Manager | Phase 2 candidates: Service Mapping, advanced AIOps, additional RBA scenarios, SIEM integration
Formal ECS engagement closeout | Document what was built, what is operating, and what Phase 2 will add; sign off with IT Manager | This document is the foundation for the Phase 2 SOW

## R&R
08 — Hypercare and Maturity — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
30-day checkpoint facilitation | R | C | ECS leads; Service Desk Manager and designated admin attend
KPI data pull for checkpoints | R | I | ECS pulls from PA dashboard; customer reviews
Tuning actions implementation | R | C | ECS implements agreed tuning actions; customer admin observes for knowledge transfer
Operator maturity pulse check (survey) | R | I | ECS administers and reports; Service Desk Manager reviews results
Phase 2 scope definition | R | C | ECS drafts based on production data; IT Manager approves scope
Formal engagement closeout sign-off | C | R | Customer IT Manager signs off; ECS prepares the closeout document
Ongoing Event Management administration post-closeout | I | R | Customer designated admin owns; ECS available for Phase 2 engagement

## Consultant Guide
08 — Hypercare and Maturity — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The 90-Day Window Is Everything
Event Management programs that are not actively managed in the first 90 days stabilize at 60–70% of their potential. The suppression rules never get tuned. The correlation windows never get calibrated. The AIOps model never gets enough operator feedback. Schedule the 30/60/90-day checkpoints before go-live, not after. Put them in the project plan as deliverables, not optional check-ins.
The Named Admin Is the Program
The designated Event Management admin is the difference between a program that evolves and one that fossilizes. Find this person before go-live. Give them the evt_mgmt_admin role. Walk them through every rule, every threshold, every workflow. The training session is not optional — it is the knowledge transfer that makes the program sustainable.
Phase 2 Is Sold at the 90-Day Checkpoint
The 90-day checkpoint is the best time to scope Phase 2. The customer has 90 days of production data and can see exactly what is working and what is not. ECS has the credibility of a successful go-live. The IT Manager is engaged with the program results. This is the natural moment to say: 'Based on what we have built and what we can see in the data, here is what Phase 2 should include.'
Document the Escalation Criteria Explicitly
Before go-live, get written agreement from the IT Manager on the escalation criteria (the thresholds above). This protects both ECS and the customer. When the 30-day checkpoint shows CI correlation at 78%, there is no ambiguity — it is below the 75% escalation threshold, a formal review is triggered, and ECS is engaged. Without agreed escalation criteria, every sub-target measurement becomes a negotiation.

## Adoption vs Re-engineering
08 — Hypercare and Maturity — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
'We do not need the 90-day hypercare structure — our team will manage it.' | Engage in the three checkpoint structure regardless of the customer's confidence level. Checkpoints are lightweight (2 hours each) and the data they produce is essential for Phase 2 scoping. | Every Event Management program that skips hypercare checkpoints has the same outcome: the program is declared successful at go-live and then quietly ignored until a major incident reveals the gaps. | 'The checkpoints take 2 hours each and give you 90 days of trend data for the Phase 2 conversation. That data is worth more than the 6 hours — it is what makes Phase 2 a no-brainer approval.' | Only if the customer is a highly mature ServiceNow shop with an existing admin team and proven self-sufficiency on other platform areas.

## ServiceNow Mapping
08 — Hypercare and Maturity — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Hypercare Measurement Sources
CI correlation rate | PA indicator on em_alert table | Correlated alerts / total alerts; trend weekly
Alert promotion rate | PA indicator on em_alert + task tables | Promoted incidents / Sev 1-2 alerts; trend weekly
Operator feedback rate | ml_operator_feedback table | Accept + dismiss counts; ratio is model quality indicator
MID Server queue depth | ecc_queue count (input queue) | Monitor daily; alert if > 1,000 during non-storm periods
2. OOTB Tuning Capabilities
Correlation window adjustment | em_correlation_rule.time_window | Adjust per rule; requires ECS or designated admin
Storm threshold adjustment | em_correlation_rule.count_threshold | Increase if false storm alerts; decrease if real storms are missed
Suppression rule expansion | em_event_rule (suppression type) | Add new suppression rules from Event Triage queue analysis
AIOps sensitivity tuning | Predictive AIOps > Administration > Sensitivity | Reduce sensitivity if too many false positives; increase if too many misses