## Instructions
02 — Article Template Standards
Knowledge Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the OOTB article templates — the structured format every KB article must follow. Consistent templates make articles searchable, Virtual Agent-readable, and maintainable. Unstructured articles written in freeform prose are the primary cause of poor KB search results.
Who fills this out | ECS SA owns this workbook. Customer Knowledge Managers review and approve before article authoring begins.
Sprint window | Sprint 5 Week 1
Estimated effort | 1–2 hours
Related workbooks | 01 KB Structure · 04 Article Workflow
Success criteria
• | OOTB article templates defined for at least two article types (How-To, Known Error/Workaround).
• | Template fields are documented and agreed.
• | Every MVP article uses the appropriate template.
• | Template compliance is part of the Knowledge Manager review checklist.

## Process Decisions
02 — Article Template Standards — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which article types should have templates at MVP? | Two OOTB templates: How-To (step-by-step instructions for end users) and Known Error/Workaround (IT Staff KB — issue description, impact, workaround, fix ETA). |  | Two templates cover 90% of knowledge content. Templates ensure Virtual Agent can parse article structure for automated answers.
2 | Should articles use the OOTB Knowledge Article workflow or a custom approval process? | OOTB workflow: Draft → Review → Published → Retired. No custom approval steps. Knowledge Manager is the reviewer and publisher. |  | Custom approval workflows add days to article publication and are rarely enforced consistently. The OOTB review-and-publish pattern with a named KM is faster and equally rigorous.
3 | What is the mandatory field set for every article? | Mandatory: Short Description (used as article title in search), Knowledge Base, Category, Valid to (review date — maximum 12 months from publish). Optional but strongly recommended: Flagged for review date, Related catalog items. |  | The Valid to date is the most important field for KB health. Without it, articles stay published indefinitely and become stale.

## Dependencies
02 — Article Template Standards — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | KB Structure (Workbook 01) confirmed | Required | Customer | Sprint 5 Wk 1

## Configuration Data
02 — Article Template Standards — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. How-To Article Template Fields
Short Description | Action verb + object e.g., 'Request a new laptop' or 'Reset your password' | Used as article title in search. No jargon.
Article body — Section 1: Overview | One paragraph: what this article helps you do.
Article body — Section 2: Before you start | Prerequisites (accounts, access, information needed).
Article body — Section 3: Steps | Numbered steps. Maximum 10. Each step = one action.
Article body — Section 4: Need more help? | Link to catalog item or contact information.
Valid to (review date) | 12 months from publish date | KM reviews and extends or retires.
Related catalog items | Link to the catalog item this article supports (if applicable)
2. Known Error / Workaround Template Fields
Short Description | Issue description in user language e.g., 'VPN disconnects after 30 minutes'
Issue description | What happens; who is affected; when it started.
Workaround | Step-by-step workaround. Must be immediately actionable.
Fix ETA | Estimated resolution date or 'Under investigation'
Severity | Major / Minor
Valid to | 90 days (Known Errors resolve faster than How-Tos)

## R&R
02 — Article Template Standards — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Design and document article templates | R/A | I | ECS SA.
Review and approve templates | I | R/A | Customer Knowledge Managers.
Configure OOTB templates in ServiceNow | R/A | I | ECS SA.
Validate first 5 articles against template standards | R/A | C | ECS reviews; KM confirms quality.

## Consultant Guide
02 — Article Template Standards — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Template enforcement
Templates are only effective if the Knowledge Manager enforces them during article review. Build the template compliance check into the KM review checklist (Workbook 04): does the article use the correct template? Is the Valid to date set? Is the short description search-friendly? These three checks take 2 minutes per article and prevent the KB from degrading into freeform prose over time.

## Adoption vs Re-engineering
02 — Article Template Standards — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want authors to write articles in their own format | Enforce OOTB templates for all MVP articles. | Freeform articles produce poor search results and cannot be parsed by Virtual Agent for automated answers. Template structure is the minimum for a machine-readable KB. | 'Authors can absolutely write in their own voice and style — the template just provides the structure. Think of it as a form: the author fills in the steps, the overview, and the valid-to date. The structure is invisible to the reader but critical for search and Virtual Agent.' | Only for long-form reference content (policy documents, architecture guides) where template structure would be forced. Still require Short Description and Valid to fields.

## ServiceNow Mapping
02 — Article Template Standards — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Article Configuration
Knowledge Article | kb_knowledge | Main article table.
Article Template | kb_template | OOTB article templates — configure here.
Valid to field | kb_knowledge.valid_to | Review date. OOTB KB health flags expired articles.