## Instructions
05 — Search Optimization
Knowledge Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the OOTB search configuration for the Knowledge Base: search source priority, synonyms, and the article field weighting that determines which articles appear at the top of search results. Good search is the single biggest driver of KB adoption — users who can't find what they need in two searches go to the helpdesk instead.
Who fills this out | ECS SA configures; customer Knowledge Manager validates search results for the top 10 expected search terms.
Sprint window | Sprint 5 Week 2
Estimated effort | 2–3 hours (configuration + validation with KM)
Related workbooks | 01 KB Structure · 02 Article Template Standards
Success criteria
• | OOTB Knowledge search source is configured and indexed.
• | Short Description field has highest search weight (it is the article title).
• | Top 10 expected search terms return relevant results.
• | Search synonyms are configured for common IT terminology variations.
• | No deprecated or retired articles appear in search results.

## Process Decisions
05 — Search Optimization — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which article fields should be indexed for search? | Short Description (highest weight), Text (article body, medium weight), Keywords/Tags (medium weight). Do not index internal fields like Author or Workflow State. |  | The Short Description is effectively the article title — it should have the highest search weight. Article body catches long-tail search terms. Keywords/Tags allow authors to add synonyms for their articles.
2 | Should we configure search synonyms? | Yes. Configure OOTB Search Synonyms for the 10 most common terminology variations: VPN = 'remote access', 'password reset' = 'forgot password', 'laptop' = 'computer' = 'device'. Start with 10; expand based on search analytics post-launch. |  | Search synonyms prevent users from not finding articles because they used a different word than the author. A user who searches 'forgot password' and gets no results when the article is titled 'Reset your password' gives up and calls the helpdesk.
3 | How should retired and expired articles be handled in search? | Retired articles must be excluded from search results immediately upon retirement. Articles past their Valid to date but not yet reviewed should remain in search results — they may still be accurate. OOTB search automatically excludes articles with workflow_state = Retired. |  | Users finding retired article links from bookmarks or external search engines should see a redirect to the KB homepage, not a broken page. Configure OOTB redirect on retired articles.

## Dependencies
05 — Search Optimization — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Articles published in KB (at least MVP set) | Required | Customer KMs | Sprint 5 Wk 2 | Cannot validate search results without published content.

## Configuration Data
05 — Search Optimization — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Search Source Configuration
Knowledge search source | OOTB: sp_search_source for Knowledge | Configure in Service Portal > Search Sources.
Short Description weight | 10 (highest) | OOTB default. Do not reduce.
Text (article body) weight | 5 (medium)
Keywords/Tags weight | 7 (high) | Authors use Keywords field to add synonyms for their articles.
Retired articles in search | Excluded — OOTB (workflow_state filter) | No configuration needed — OOTB behaviour.
2. Search Synonyms (MVP set — top 10)
password reset | forgot password; locked out; can't log in
VPN | remote access; remote work; connect from home
laptop | computer; device; notebook; MacBook
software install | application; program; app request
access request | permissions; account access; user access
Additional synonyms | [Customer KM to add based on helpdesk ticket language] | Review the top 20 helpdesk ticket subjects for synonym candidates.

## R&R
05 — Search Optimization — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Configure search source and field weights | R/A | I | ECS SA.
Configure search synonyms (MVP set) | R/A | C | ECS SA configures initial set; KM adds domain-specific terms.
Validate top 10 search terms return relevant results | R | A | ECS tests; KM validates results are correct.
Review search analytics monthly and add synonyms | I | R/A | Customer KM owns ongoing synonym expansion.

## Consultant Guide
05 — Search Optimization — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The synonym seed list
The best source for search synonyms is not a brainstorming session — it is the existing helpdesk ticket short description field. Export the top 50 most common ticket subjects from the last 6 months, identify the language users use for common requests, and configure synonyms that map that language to the KB article titles. This produces immediately relevant synonyms based on actual user behaviour.

## Adoption vs Re-engineering
05 — Search Optimization — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want to use a third-party search engine instead of OOTB | Use OOTB search with configured weights and synonyms. | Third-party search engines require integration maintenance and lose OOTB KB Health analytics, Virtual Agent integration, and Now Assist semantic search capabilities. | 'OOTB search with the right field weights and synonyms provides very good results for most corporate KB environments. If you have specific search quality issues at 6 months post-launch, we can revisit with Now Assist semantic search — which is still OOTB, just an upgraded tier.' | OOTB search first. Now Assist semantic search (if licensed) is the Phase 2 upgrade path, not a custom third-party engine.

## ServiceNow Mapping
05 — Search Optimization — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Search Configuration
Search Source | sp_search_source | Configure in Service Portal > Search Sources.
Search Synonym | ts_synonym | Search synonyms table. Configure in Knowledge > Administration > Search Terms.
Typeahead Search | ts_index_table | OOTB typeahead suggestions. Populated automatically as users search.