## Instructions
06 — Knowledge KPIs & Governance
Knowledge Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Defines the Knowledge Management KPIs, the monthly governance cadence, and the process for measuring KB contribution to helpdesk deflection. Without measured outcomes, knowledge management becomes an unfunded activity that degrades over time.
Who fills this out | ECS SA defines the KPI framework; Customer KM and IT Director agree the targets.
Sprint window | Sprint 5 Week 2
Estimated effort | 1–2 hours
Related workbooks | 04 Article Workflow
Success criteria
• | KB deflection rate is baselined at go-live (helpdesk tickets with KB article linked).
• | Monthly KB health review is scheduled with named owner.
• | Article count and freshness targets are agreed.
• | Search abandon rate is tracked (users who searched and submitted a ticket anyway).

## Process Decisions
06 — Knowledge KPIs & Governance — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What is the primary KPI for Knowledge Management success? | Deflection rate: % of helpdesk tickets where a KB article was viewed before or during the ticket lifecycle. Secondary: article freshness (% with Valid to date set and not expired). |  | Deflection rate directly measures the business value of the KB. Every ticket deflected saves approximately 15–30 minutes of helpdesk time. A KB with 100 articles deflecting 20% of tickets saves more time than a KB with 500 articles that nobody uses.
2 | How do we measure deflection? | OOTB: track 'Viewed Knowledge' flag on incident/request records. ServiceNow automatically sets this flag when a user views a KB article before submitting a ticket. Report monthly on: tickets with KB viewed vs. total tickets. |  | The OOTB deflection mechanism requires no customisation — it is built into the Service Portal and Employee Center knowledge search. Configure the monthly deflection report in Sprint 5 and baseline it at go-live.

## Dependencies
06 — Knowledge KPIs & Governance — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | KB articles published (MVP set) | Required | Customer KMs | Sprint 5 Wk 2
2 | Performance Analytics scope (if PA in scope) | Recommended | ECS SA | Sprint 5 | PA dashboards provide richer KB analytics than standard reports.

## Configuration Data
06 — Knowledge KPIs & Governance — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. KPI Targets
Deflection rate target (6 months post-launch) | 15% of tickets have KB article viewed before submission | Baseline at go-live; review monthly.
Article freshness target | 90% of published articles with Valid to date set and not expired
Monthly article review completion | 100% of Needs Review articles actioned within 30 days of expiry
New article creation rate | Minimum 2 new articles per KB per month for first 6 months | Keeps KB growing; review target at 6 months.
2. Governance Cadence
Monthly KB health review | 1st of each month — KM reviews OOTB KB Health report
Quarterly deflection review | KM + IT Director review deflection rate quarterly
Annual KB audit | Full review of all published articles; retire stale content

## R&R
06 — Knowledge KPIs & Governance — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Configure KB deflection report | R/A | I | ECS SA.
Set KPI targets | C | R/A | Customer KM + IT Director.
Run monthly KB health review | I | R/A | Customer KM.
Report KB deflection to IT Director quarterly | I | R/A | Customer KM.

## Consultant Guide
06 — Knowledge KPIs & Governance — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
The deflection conversation
KB deflection rate is the only metric that directly connects Knowledge Management investment to business value. Frame it for the IT Director: 'For every 10% of tickets deflected by the KB, your helpdesk handles 10% fewer tickets for the same cost. At your current ticket volume, that is X tickets per month. At 15 minutes per ticket, that is Y hours saved per month.' Put a number on it in Sprint 5 — it justifies the knowledge management investment and motivates the KM.

## Adoption vs Re-engineering
06 — Knowledge KPIs & Governance — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We don't have time for a monthly KB review | Schedule the monthly review as a standing 30-minute calendar appointment for the KM. | Without a standing review appointment, the KB review happens 'when there's time' — which is never. 30 minutes per month is the minimum investment to prevent KB degradation. | '30 minutes once a month to review a report and click Extend or Retire on a few articles. That is the entire governance commitment. Without it, the KB is accurate at launch and misleading users within 12 months. With it, the KB gets better every month.' | Never skip the governance cadence. Simplify it for small teams, but never eliminate it.

## ServiceNow Mapping
06 — Knowledge KPIs & Governance — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. KB Analytics
Deflection flag | incident.knowledge_accessed / sc_request.knowledge_accessed | OOTB flag set when user views KB before submitting.
KB Health Dashboard | Knowledge > Administration > KB Health | Article freshness, stale count, review queue.
Search Analytics | Knowledge > Administration > Search Analytics | What users searched for; what they found; where they gave up.