## Instructions
01 -- Now Assist Scope & Entitlement
Now Assist / GenAI Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Confirm Now Assist for ITSM entitlement, define which GenAI skills to activate at go-live, and establish the OOTB-first boundaries for the 18-week scope.
Who fills this out | ECS Consultant leads. Customer IT Director and ITSM Process Owner confirm entitlement and scope decisions.
Sprint window | Sprint 5 -- scope locked by end of Week 9
Estimated effort | 2-3 hours with Customer IT Director
Related workbooks | 02 Text Summarization · 03 Search Augmentation · 04 Resolution Notes · AP-16 Virtual Agent · AP-17 Predictive Intelligence
Success criteria
• | Now Assist for ITSM license confirmed and activated.
• | GenAI skills to activate at go-live agreed (max 3 for 18-week scope).
• | Now Assist Admin named (can be same as VA Admin).
• | Data privacy and content filtering settings reviewed with customer.
• | AI Search index scope confirmed.

## Process Decisions
01 -- Now Assist Scope & Entitlement — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which Now Assist skills should be activated at go-live? | Three OOTB skills: (1) Incident Summarization, (2) Resolution Notes Generation, (3) Now Assist Search (AI Search). Virtual Agent (AP-16) is separately scoped. |  | These three deliver the highest immediate agent productivity value with the lowest configuration overhead. Case Summarization (CSM) and GenAI for Change are Phase 2.
2 | Should Now Assist generate content automatically or on agent demand? | On agent demand only (OOTB default). Agent clicks Generate to trigger AI output. |  | On-demand preserves agent control and avoids unwanted AI content appearing in records. Automatic generation is a Phase 2 setting after agents are comfortable with quality.
3 | How should AI-generated content be labeled in the UI? | OOTB AI badge is enabled -- all AI-generated text is visibly labeled. Do not disable the badge. |  | Regulatory and policy environments (especially federal) require clear disclosure of AI-generated content. The OOTB badge satisfies this requirement.
4 | Should Now Assist Search replace or augment the existing search bar? | Augment -- AI Search results appear alongside standard search results (OOTB). Do not disable standard search. |  | AI Search improves relevance but can miss exact-match queries where keyword search excels. Both run in parallel OOTB.
5 | What data does Now Assist send to the AI model? | Only field values from the incident/request record in scope. No external data leaves the instance unless explicitly configured. |  | ServiceNow Now Assist uses a managed LLM (Azure OpenAI via ServiceNow's infrastructure). Customer data is not used to train the base model. Review with Customer CISO before Sprint 5.

## Dependencies
01 -- Now Assist Scope & Entitlement — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Now Assist for ITSM license | Required | Customer | Before Sprint 5 | Cannot activate any Now Assist skill without entitlement confirmed.
2 | Now Platform Tokyo or later (Washington DC recommended) | Required | Customer IT | Before Sprint 5 | Now Assist skills require Washington DC release minimum.
3 | CISO/Privacy review of Now Assist data handling | Required | Customer CISO | Before Sprint 5 | Federal customers must confirm AI data handling complies with their ATO/privacy policy.
4 | Published KB articles (AP-13) | Required | ECS | Sprint 5 Wk 1 | AI Search indexes published KB articles -- without them search has nothing to augment.
5 | Incidents with resolution notes in history | Recommended | Customer | Sprint 5 Wk 1 | Resolution Notes Generation quality improves with a corpus of past good resolution notes.

## Configuration Data
01 -- Now Assist Scope & Entitlement — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Now Assist Activation
Now Assist for ITSM skill -- Incident Summarization | Activate Sprint 5 Wk 1 | Summarizes incident work notes and comments for agents and stakeholders
Now Assist for ITSM skill -- Resolution Notes Generation | Activate Sprint 5 Wk 1 | Generates draft resolution notes from incident history
Now Assist Search (AI Search) | Activate Sprint 5 Wk 1 | Semantic search across KB, catalog, and incidents
Case Summarization (CSM) | Defer to Phase 2 | Out of scope for ITSM-focused 18-week engagement
GenAI for Change | Defer to Phase 2 | Change assessment generation needs mature Change process first
2. Governance Settings
AI badge on generated content | Enabled (OOTB default -- do not disable) | Required for transparency and federal compliance
On-demand vs. automatic generation | On-demand (agent clicks Generate) | Preserves agent control; automatic is Phase 2
Content filtering | Enabled -- OOTB responsible AI filters active | Do not disable content filtering in any federal deployment
Data sent to LLM | Incident fields in scope only -- no PII beyond what is in the record | Review with Customer CISO before activation

## R&R
01 -- Now Assist Scope & Entitlement — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Confirm Now Assist license entitlement | I | R/A | Customer IT Director.
CISO data handling review | I (provide documentation) | R/A | Customer CISO.
Activate Now Assist skills in instance | R/A | I | ECS Consultant.
Name Now Assist Admin | I | R/A | Customer IT Director.
Communicate AI tool availability to agents | Review | R/A | Customer IT Manager sends comms.

## Consultant Guide
01 -- Now Assist Scope & Entitlement — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Federal CISO conversation
Many federal customers have ATO requirements that need to be reviewed before any AI tool is enabled. ServiceNow publishes a Now Assist Security and Privacy whitepaper -- share this with the Customer CISO before Sprint 5. Do not activate Now Assist without written confirmation from the CISO or their delegate.
Three skill limit rationale
Three OOTB skills in 2 sprints is the right scope ceiling. Each skill needs configuration, agent training, and UAT. More than three skills in the 18-week window spreads attention too thin and produces lower adoption across all skills.
AI badge requirement
Never advise disabling the AI badge. The OOTB disclosure badge is not optional for responsible deployment -- especially in federal environments where AI-generated content in records may have downstream legal or audit implications.

## Adoption vs Re-engineering
01 -- Now Assist Scope & Entitlement — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want Now Assist to automatically update records | On-demand at go-live; auto-generation after agent trust is established. | Auto-generation in Sprint 5 means AI content appears before agents understand its quality. Trust must be built first. | Starting on-demand means every agent sees Now Assist in action before anything is automatically written to a record. Once agents trust the output quality -- which typically takes 3-4 weeks -- we can enable automatic generation for specific skills like resolution notes. We do not skip the trust-building phase. | After 30 days of on-demand use with positive agent feedback.

## ServiceNow Mapping
01 -- Now Assist Scope & Entitlement — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Now Assist Core
sn_now_assist | Now Assist skill configuration table | sn_now_assist
sn_now_assist_skill | Individual skill records (summarize, generate, search) | sn_now_assist_skill
Now Assist Admin Console | OOTB admin console -- skill activation, monitoring, content filtering | Now Assist > Admin Console