## Instructions
02 -- Incident & Case Summarization
Now Assist / GenAI Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Configure the OOTB Now Assist Incident Summarization skill to generate concise summaries of incident work notes and comments for agents and stakeholders.
Who fills this out | ECS Consultant configures. Customer Service Desk Lead and agents review during UAT.
Sprint window | Sprint 5 -- skill active and tested by end of Week 10
Estimated effort | 3-4 hours including configuration and agent UAT
Related workbooks | 01 Now Assist Scope · 04 Resolution Notes Generation
Success criteria
• | Incident Summarization skill active on Incident form.
• | Generate Summary button visible to agents on open incidents.
• | Summary output tested on at least 10 real incidents.
• | AI badge visible on all generated summaries.
• | Agent UAT sign-off from Service Desk Lead.

## Process Decisions
02 -- Incident & Case Summarization — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What should the summary include? | OOTB: most recent 5 work notes + caller description + current state. Do not customize the prompt template in 18-week scope. |  | The OOTB prompt is tuned for incident context. Custom prompts require testing and iteration that is not scoped for Sprint 5.
2 | Who can generate a summary -- agents only or also customers? | Agents and IT staff only (OOTB default). Do not expose summary generation to the employee portal in 18-week scope. |  | Customer-facing summarization adds content review requirements. Agent-facing is the safe starting point.
3 | Should summaries be saved to the incident record? | Optional -- agent can copy summary to work notes. Do not auto-write to resolution field. |  | Auto-write to resolution field bypasses agent review. Agent copy-and-edit preserves accountability and improves summary quality through light editing.
4 | Should major incident stakeholders receive AI summaries? | Yes for Major Incidents (P1/P2) -- enable the OOTB Major Incident Stakeholder Summary feature. |  | This is one of the highest-value use cases: automatically drafting stakeholder update emails during a major incident saves the incident manager 15-30 minutes per update cycle.

## Dependencies
02 -- Incident & Case Summarization — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Now Assist for ITSM activated (WB1) | Required | ECS | Sprint 5 Wk 1 | Summarization skill requires Now Assist active.
2 | Incidents with 3+ work notes in history | Recommended | Customer | Sprint 5 Wk 1 | Summarization quality requires sufficient work note history to summarize.

## Configuration Data
02 -- Incident & Case Summarization — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Summarization Skill Configuration
Skill | Summarize Incident (OOTB Now Assist skill) | Select from Now Assist skill library -- no custom LLM prompt
Trigger | On-demand -- agent clicks Generate Summary button | Button appears on Incident form header
Input scope | Work notes (last 5) + short description + description | OOTB default input scope
Output placement | Inline summary panel below incident header (OOTB) | Do not add a custom field for summary storage
AI badge | Enabled (OOTB -- do not disable) | All generated summaries display AI badge
Auto-save to record | Disabled -- agent copies manually if desired | Preserves agent review and accountability
2. Major Incident Stakeholder Summary
Enable for P1/P2 | Yes -- OOTB Major Incident Stakeholder Update feature | Generates draft stakeholder email from current incident state
Recipient list | IT Director, affected business owners | Customer to confirm distribution list
Cadence | On-demand -- Major Incident Manager generates at each update cycle | Typically every 30-60 minutes during active P1

## R&R
02 -- Incident & Case Summarization — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Configure Incident Summarization skill | R/A | I | ECS Consultant.
Enable Major Incident stakeholder summary | R/A | Confirm P1/P2 distribution list | ECS configures; Customer IT Manager provides list.
UAT -- 10 incident summaries reviewed by agents | R | A | ECS facilitates; Service Desk Lead signs off.
Agent briefing on summarization skill | R/A | Attend | ECS delivers 30-min briefing with live demo.

## Consultant Guide
02 -- Incident & Case Summarization — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
UAT selection criteria
Choose UAT incidents that vary in length and complexity: 2 short incidents (1-2 work notes), 4 medium (3-5 work notes), 4 long (10+ work notes). Long incidents show the highest summarization value and are most convincing for agents who are skeptical.
Major Incident pitch
The major incident stakeholder summary is often the single most compelling Now Assist demo for IT leadership. Run a live demo during Sprint 5 kickoff: pull a real historical P1, click Generate, show the stakeholder email draft. Leadership buys in immediately.
Quality calibration
Now Assist summaries are drafts. Coach agents that light editing is expected -- the AI saves 80% of the writing time, not 100%. Agents who expect perfection become disappointed; agents who expect a strong draft become advocates.

## Adoption vs Re-engineering
02 -- Incident & Case Summarization — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want summaries emailed automatically to managers | On-demand Major Incident summary with agent review before send. | Auto-email without review risks sending inaccurate AI content to leadership. Review step is mandatory. | The Major Incident Manager reviews the AI draft -- which takes 30 seconds -- and clicks Send. We save the writing time and preserve the human verification step. That combination is exactly what responsible AI use looks like in a federal environment. | Never auto-send AI-generated content to stakeholders without review.

## ServiceNow Mapping
02 -- Incident & Case Summarization — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Summarization
sn_now_assist_skill (Summarize) | Now Assist summarization skill record | sn_now_assist_skill
incident (work_notes) | Source field for summarization input | incident.work_notes
Major Incident Management | OOTB MIM module -- stakeholder update feature | em_alert, major_incident_state