## Instructions
03 -- Now Assist Search (AI Search Augmentation)
Now Assist / GenAI Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Configure OOTB Now Assist Search to augment the ServiceNow search experience with semantic AI results across KB articles, catalog items, and incidents.
Who fills this out | ECS Consultant configures search index scope. Customer KB Admin confirms content quality for indexing.
Sprint window | Sprint 5 -- AI Search active and tested by end of Week 10
Estimated effort | 3-4 hours including index configuration and search quality UAT
Related workbooks | 01 Now Assist Scope · AP-13 Knowledge Management · AP-CAT Service Catalog · AP-15 Employee Center
Success criteria
• | Now Assist Search active in Employee Center and Service Portal.
• | Search index includes KB articles, catalog items, and incidents (read-only).
• | AI-generated answer panel appears above standard results for relevant queries.
• | No-results fallback configured (VA or help desk link).
• | UAT: 20 search queries tested across IT and HR topics.

## Process Decisions
03 -- Now Assist Search (AI Search Augmentation) — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What content should AI Search index? | KB articles (all published) + catalog items (all published) + incidents (closed, for agent search only). |  | Published content ensures quality. Closed incidents are indexed only for agent-facing search -- not for employee portal. Draft or unpublished content must not be indexed.
2 | Should AI Search appear in the employee portal or only for agents? | Both -- employee-facing in Employee Center, agent-facing in Service Portal and Agent Workspace. |  | Employee Center search is the primary deflection channel. AI Search improves first-click resolution rates significantly.
3 | Should AI Search display a generated answer or just results? | Generated answer panel (OOTB) appears above search results when confidence is high. Always show underlying source links. |  | Generated answers without source links create trust issues. OOTB always shows the source article alongside the AI answer.
4 | What happens when AI Search finds no relevant results? | OOTB no-results fallback: display a link to Virtual Agent or a Create Ticket catalog item. |  | Dead-end searches increase help desk call volume. VA or ticket creation as fallback preserves the deflection opportunity.

## Dependencies
03 -- Now Assist Search (AI Search Augmentation) — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Now Assist for ITSM activated (WB1) | Required | ECS | Sprint 5 Wk 1 | AI Search requires Now Assist active.
2 | KB articles published (AP-13) | Required | ECS + Customer | Sprint 5 Wk 1 | Empty KB = empty AI Search results.
3 | Employee Center live (AP-15) | Required | ECS | Sprint 5 Wk 1 | AI Search is embedded in the Employee Center search bar.
4 | Catalog items published (AP-CAT) | Required | ECS | Sprint 5 Wk 1 | Catalog items must be published to appear in AI Search results.

## Configuration Data
03 -- Now Assist Search (AI Search Augmentation) — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Search Index Scope
KB articles | All published articles -- all indexed knowledge bases | Draft articles excluded automatically
Catalog items | All published catalog items | Unpublished items excluded
Incidents (agent search) | Closed incidents -- agent-facing only | Employee portal does not surface incident records
Employee portal incident access | Disabled -- employees cannot search incident records | Privacy and data segregation requirement
2. Search UI Configuration
AI answer panel | Enabled -- appears above results when confidence is high (OOTB) | Source article link always shown alongside AI answer
Confidence threshold for AI answer | 0.75 (OOTB default) | Below this threshold, AI answer panel is suppressed
No-results fallback | Link to Virtual Agent OR Create Ticket catalog item | Customer to confirm preferred fallback action
Search bar location | Employee Center global search bar (OOTB integration) | No custom search widget needed

## R&R
03 -- Now Assist Search (AI Search Augmentation) — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Configure Now Assist Search index scope | R/A | I | ECS Consultant.
Verify KB article quality before indexing | I | R/A | Customer KB Admin confirms article quality.
Enable AI Search in Employee Center | R/A | I | ECS enables; Customer PM witnesses.
UAT -- 20 search queries tested | R | A | ECS facilitates; Customer Service Desk Lead and HR rep validate.
Configure no-results fallback | R/A | Confirm fallback preference | ECS configures; Customer decides VA vs. Create Ticket.

## Consultant Guide
03 -- Now Assist Search (AI Search Augmentation) — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Content quality is everything
AI Search is only as good as the content it indexes. Before activating, audit the KB: remove articles with broken links, outdated procedures, or placeholder text. One bad article surfaced prominently in AI Search does more damage to adoption than no AI Search at all.
UAT query design
Write 20 UAT queries that mirror real employee search language: 'how do I reset my password', 'request a new laptop', 'who is my HR contact', 'VPN not working', 'onboarding checklist'. Use actual phrasing from help desk tickets, not technical terms. This tests real-world relevance.
Source link discipline
Coach the team: AI Search answers are always drafts that cite a source. The answer gets the employee 80% of the way there. The source link provides the authoritative detail. Never frame AI Search as replacing the KB article -- frame it as surfacing it faster.

## Adoption vs Re-engineering
03 -- Now Assist Search (AI Search Augmentation) — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Replace our SharePoint knowledge base with AI Search | Index ServiceNow KB articles only. SharePoint migration is out of scope. | SharePoint indexing requires a custom connector not in OOTB Now Assist. It is a Phase 2 integration project. | AI Search works on what is in ServiceNow. The best accelerator for AI Search quality is migrating your top 20 most-searched articles from SharePoint into the ServiceNow KB. We scoped that migration in AP-13. Phase 2 can bring in the full SharePoint corpus once the ServiceNow KB is the primary destination. | Phase 2 -- SharePoint connector after KB migration is proven.

## ServiceNow Mapping
03 -- Now Assist Search (AI Search Augmentation) — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. AI Search
sn_ais_search | AI Search configuration -- index scope, confidence settings | sn_ais_search
kb_knowledge | KB articles indexed by AI Search | kb_knowledge
sc_cat_item | Catalog items indexed by AI Search | sc_cat_item
Employee Center search bar | AI Search integrated into EC global search OOTB | sp_search_source