## Instructions
04 -- Resolution Notes & Work Note Generation
Now Assist / GenAI Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Configure the OOTB Now Assist Resolution Notes Generation skill to help agents draft resolution notes and work note updates from incident history.
Who fills this out | ECS Consultant configures. Customer Service Desk Lead reviews quality during UAT.
Sprint window | Sprint 5-6 -- skill active by end of Week 11
Estimated effort | 2-3 hours including configuration and UAT
Related workbooks | 01 Now Assist Scope · 02 Incident Summarization
Success criteria
• | Resolution Notes Generation skill active on Incident form.
• | Generate Resolution Notes button visible when incident is in Resolved state.
• | Output quality reviewed on 10 test incidents by Service Desk Lead.
• | AI badge visible on all generated resolution notes.
• | Agent coaching delivered -- 'draft, not final' framing established.

## Process Decisions
04 -- Resolution Notes & Work Note Generation — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | When should the Generate Resolution Notes button appear? | Only when incident is in Resolved or Pending state. Not on open incidents. |  | Resolution notes are written at close. Showing the button on open incidents creates confusion about when to use it.
2 | Should generated notes auto-populate the Resolution Notes field? | No -- generated notes appear in a preview panel. Agent copies and edits before saving. |  | Auto-populate bypasses agent review. Given federal audit requirements, agents must own the resolution note content.
3 | Should the skill also generate work note updates during resolution? | Yes -- enable the Work Note Draft skill as a companion to Resolution Notes. |  | Mid-resolution work notes benefit from summarization too. The OOTB skill supports both use cases.
4 | How should the resolution note quality improve over time? | Agent edits are captured as implicit feedback. No explicit rating system needed in 18-week scope. |  | OOTB implicit feedback from agent edits is sufficient for quality improvement. Explicit rating UI adds configuration scope.

## Dependencies
04 -- Resolution Notes & Work Note Generation — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Now Assist for ITSM activated (WB1) | Required | ECS | Sprint 5 Wk 1 | Resolution Notes skill requires Now Assist active.
2 | Incident Summarization active (WB2) | Recommended | ECS | Sprint 5 Wk 1 | Summarization and Resolution Notes share the same LLM call pattern -- activate together.
3 | Incidents with good historical resolution notes | Recommended | Customer | Sprint 5 Wk 1 | The LLM uses incident work notes as input -- richer work notes = better generated output.

## Configuration Data
04 -- Resolution Notes & Work Note Generation — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Resolution Notes Generation Skill
Skill | Generate Resolution Notes (OOTB Now Assist skill)
Trigger state | Resolved or Pending (OOTB event-based display) | Button hidden on Open/In Progress incidents
Input scope | All work notes + short description + category + resolution code | More context = better generated notes
Output placement | Preview panel -- agent copies to Resolution Notes field | Do not auto-populate the field
AI badge | Enabled (OOTB -- do not disable) | Visible on all generated content
2. Work Note Draft Skill
Enable work note draft | Yes -- OOTB companion skill to Resolution Notes | Helps agents draft progress updates mid-resolution
Trigger | On-demand -- agent clicks Draft Work Note | Available on all open incidents
3. Quality Coaching
Agent framing | Now Assist generates a draft -- agents review, edit, and own the final note | Establish this framing in agent briefing before go-live
Edit expectation | Agents should expect to edit 20-40% of generated content | Editing is not a failure -- it is the intended workflow

## R&R
04 -- Resolution Notes & Work Note Generation — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Configure Resolution Notes Generation skill | R/A | I | ECS Consultant.
Configure Work Note Draft skill | R/A | I | ECS Consultant.
UAT -- 10 resolution note generations reviewed | R | A | ECS + Service Desk Lead.
Agent briefing -- draft-not-final framing | R/A | Attend | ECS delivers 20-min briefing; Service Desk Lead reinforces.
Monitor resolution note quality post-go-live | N/A | R/A | Customer Service Desk Lead owns ongoing quality review.

## Consultant Guide
04 -- Resolution Notes & Work Note Generation — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Input quality lever
The quality of generated resolution notes is directly proportional to work note richness. Before go-live, coach agents to write more detailed work notes during the resolution process. Even a sentence per work note significantly improves Now Assist output.
UAT test case design
Select 10 closed incidents that vary in resolution complexity: 3 simple (password reset), 4 medium (software install, access request), 3 complex (network troubleshooting). Complex incidents show the highest value -- the AI draft saves the most time for long resolutions.
Audit trail note
For federal customers with audit requirements: AI-generated resolution notes that are agent-reviewed and saved are the agent's responsibility. The AI badge in the record shows the content was AI-assisted. This is compliant with NIST AI RMF guidance on human oversight of AI systems.

## Adoption vs Re-engineering
04 -- Resolution Notes & Work Note Generation — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Agents refuse to use AI-generated resolution notes because they feel accountable for AI errors | Frame as draft tool with explicit agent ownership. | Agent accountability concern is valid and must be addressed in training, not dismissed. | The agent is always the author of the resolution note -- Now Assist just provides the first draft. The audit trail shows the agent saved it, which means the agent reviewed and accepted it. We frame this in the briefing: you are the author, Now Assist is your research assistant. The AI badge in the record shows it was AI-assisted, which is transparent and compliant. | If accountability concern persists -- escalate to Customer CISO for AI governance clarification.

## ServiceNow Mapping
04 -- Resolution Notes & Work Note Generation — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Resolution Notes Generation
sn_now_assist_skill (Resolution Notes) | Now Assist skill for resolution note generation | sn_now_assist_skill
incident (resolution_notes) | Target field -- agent copies generated draft here | incident.resolution_notes
incident (work_notes) | Primary input to resolution note generation | incident.work_notes