## Instructions
05 -- Now Assist Adoption & KPI Measurement
Now Assist / GenAI Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Define the KPIs, OOTB dashboards, and 30/60/90-day review cadence for measuring Now Assist GenAI adoption and productivity impact.
Who fills this out | ECS Consultant configures OOTB dashboards. Customer IT Manager and Now Assist Admin own ongoing reporting.
Sprint window | Sprint 6 -- KPIs baseline at go-live; review cadence established
Estimated effort | 2 hours for dashboard setup and KPI agreement
Related workbooks | 01 Now Assist Scope · AP-19 Performance Analytics · AP-20 Reporting & Stabilization
Success criteria
• | Now Assist Admin Console analytics accessible to Customer Admin.
• | KPI baselines recorded on go-live day.
• | 30/60/90-day review meetings scheduled.
• | Agent adoption rate target agreed.
• | Continuous improvement process documented and handed over.

## Process Decisions
05 -- Now Assist Adoption & KPI Measurement — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What are the primary KPIs for Now Assist? | Skill usage rate (% of agents using each skill weekly), handle time delta, and resolution note completion rate. |  | These three measure adoption and productivity impact in terms IT leadership understands.
2 | What is a realistic adoption target? | 50% of agents actively using at least one Now Assist skill within 60 days. |  | 50% active use at 60 days is realistic for a team that received proper UAT and briefing. 100% adoption in 18 weeks is not a realistic target.
3 | How do we measure handle time improvement? | Compare average incident handle time 30 days before go-live vs. 30 days after. OOTB incident report provides this. |  | Handle time is the most tangible productivity metric. A 5-10% reduction is typical for teams actively using summarization and resolution note generation.

## Dependencies
05 -- Now Assist Adoption & KPI Measurement — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | All three Now Assist skills active | Required | ECS | Sprint 5 close | Cannot measure adoption without active skills.
2 | Now Assist Admin Console access for Customer Admin | Required | ECS | Sprint 6 Wk 1 | Admin Console is the OOTB analytics source.
3 | Handle time baseline pulled before go-live | Required | ECS | Sprint 5 close | Need pre-go-live baseline for 30-day comparison.

## Configuration Data
05 -- Now Assist Adoption & KPI Measurement — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. KPI Targets
Skill usage rate -- 30 days | 30% of agents use at least one skill per week | Early adoption benchmark
Skill usage rate -- 60 days | 50% of agents active weekly | Target for mature adoption
Handle time improvement -- 60 days | 5% reduction vs. pre-go-live baseline | Conservative; 10% is achievable with active use
Resolution note completion rate | Increase by 15% vs. baseline (more incidents closed with notes) | Now Assist lowers the barrier to writing good resolution notes
AI Search deflection contribution | 10% of employee searches result in no ticket creation (self-service) | Measured via AI Search analytics
2. Review Cadence
30-day review | ECS + Customer IT Manager -- skill usage vs. 30% target; handle time delta | ECS schedules before Sprint 6 close
60-day review | Customer IT Manager + Now Assist Admin -- confirm 50% adoption; identify low adopters | Customer-led; ECS advisory
90-day review | ECS + Customer PM -- stabilization assessment; Phase 2 GenAI scope | Marks end of ECS Now Assist obligations
3. Dashboard Access
Now Assist Admin Console | Now Assist > Admin Console > Analytics (OOTB) | No custom PA indicators in 18-week scope
Incident handle time report | OOTB Reports -- Incident > Average resolution time by period | Pull manually for 30/60/90-day comparison
Access role | sn_now_assist.admin (OOTB) | Customer Admin must have this role at go-live

## R&R
05 -- Now Assist Adoption & KPI Measurement — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Pull handle time baseline before go-live | R/A | I | ECS pulls and records baseline.
Configure Now Assist Admin Console access | R/A | Verify access | ECS configures; Customer Admin confirms.
30-day adoption review | R | A | ECS presents; Customer IT Manager reviews.
Identify and coach low adopters | I (advise) | R/A | Customer IT Manager owns agent coaching.
Phase 2 GenAI scope discussion | R (propose) | A (decide) | ECS proposes at 90-day review; Customer decides.

## Consultant Guide
05 -- Now Assist Adoption & KPI Measurement — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Handle time measurement method
Use the OOTB Reports module: Reports > New > Incident > group by month > metric = average resolve time. Run for the 30 days before go-live. Save the report. At 30 and 60 days post-launch, rerun for the same metric and compare. A simple percentage change table is all the customer needs.
Low adopter identification
The Now Assist Admin Console shows skill usage by user. At the 60-day review, identify agents with zero usage. Common causes: (1) did not attend briefing, (2) do not know the feature exists, (3) tried it once and got a poor result. Each cause has a different intervention. Zero usage is the metric to watch.
Phase 2 GenAI pipeline
At the 90-day review, present the Phase 2 GenAI roadmap: (1) GenAI for Change (change assessment generation), (2) Case Summarization (if CSM is in scope), (3) AI Search corpus expansion (SharePoint connector), (4) Proactive AI suggestions for problem management. Frame these as the next layer of value on the foundation built in Sprint 5-6.

## Adoption vs Re-engineering
05 -- Now Assist Adoption & KPI Measurement — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Why is adoption only 50% -- we expected everyone to use it | 50% at 60 days is the realistic OOTB target; 80% is achievable at 6 months. | Technology adoption follows a standard curve. 50% at 60 days represents early majority adoption. Late majority follows with peer influence and demonstrated productivity gains. | 50% adoption at 60 days means half your team is already working faster with AI assistance. The other half will follow as they see their colleagues' results. We have the usage data by agent -- we can identify the low adopters and do targeted coaching. Getting to 80% by month 6 is very achievable with that approach. | If adoption below 20% at 90 days -- structured re-training required.

## ServiceNow Mapping
05 -- Now Assist Adoption & KPI Measurement — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Analytics
Now Assist Admin Console | OOTB skill usage analytics -- usage rate, skill breakdown, user activity | sn_now_assist
Incident report (handle time) | OOTB incident report -- average resolve time by period | incident (resolved_at, opened_at)
AI Search analytics | OOTB AI Search usage and deflection metrics | sn_ais_search