## Instructions
04 -- Scorecard Configuration
Performance Analytics Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Configure the OOTB PA Scorecard for IT leadership to provide a single-page view of ITSM health against KPI targets.
Who fills this out | ECS Consultant configures OOTB scorecard. Customer IT Director reviews and approves.
Sprint window | Sprint 6 -- scorecard configured and published by Week 12
Estimated effort | 3 hours including scorecard configuration and IT Director review
Related workbooks | 01 PA Scope · 02 Indicator Library · 03 Dashboard Design
Success criteria
• | OOTB PA Scorecard published and accessible to IT Director.
• | All go-live indicators included in scorecard.
• | Green/yellow/red thresholds set and approved.
• | Scorecard scheduled for monthly review in recurring calendar invite.

## Process Decisions
04 -- Scorecard Configuration — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should the scorecard be a separate artifact or embedded in the executive dashboard? | Separate OOTB PA Scorecard document, linked from the executive dashboard. |  | The OOTB Scorecard is a formatted, printable KPI summary. It serves a different purpose than a live dashboard -- it is for leadership reviews, board presentations, and monthly reporting.
2 | How often should the scorecard be formally reviewed? | Monthly -- scheduled recurring review with IT Director and ECS PM during engagement; Customer-owned monthly review post-engagement. |  | Monthly cadence matches typical IT leadership review cycles.
3 | Should the scorecard include trend direction indicators? | Yes -- OOTB PA Scorecard shows trend arrow (up/down/flat) alongside each KPI value. |  | Trend direction tells the story faster than a raw number. 'SLA compliance 88% (down from 92%)' is more meaningful than just '88%.'

## Dependencies
04 -- Scorecard Configuration — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | OOTB indicators active with thresholds set (WB2) | Required | ECS | Sprint 6 Wk 1 | Scorecard pulls from active indicators.
2 | At least 2 weeks of collected data | Required | ECS | Sprint 6 Wk 2 | Scorecard trends are not meaningful without at least 2 data points.

## Configuration Data
04 -- Scorecard Configuration — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Scorecard Structure
Scorecard name | ITSM Monthly Health Scorecard
KPI 1: SLA Compliance % | Target: 90%. Trend: vs. prior month. | Green >90%, Yellow 80-90%, Red <80%
KPI 2: Mean Time to Resolve | Target: [Customer SLA hours]. Trend: vs. prior month. | Green at target, Yellow 10% over, Red 20% over
KPI 3: First Call Resolution Rate | Target: 70%. Trend: vs. prior month. | Green >70%, Yellow 55-70%, Red <55%
KPI 4: Incident Volume (monthly) | No target -- trend only. Shows workload change. | Used for capacity planning context
KPI 5: Open Backlog at Month End | Target: <100. Trend: vs. prior month end. | Green <100, Yellow 100-150, Red >150
2. Scorecard Governance
Scorecard owner | [Customer: IT Director name] | Owner reviews and distributes monthly
Monthly review cadence | Last Friday of each month -- recurring calendar invite | ECS PM schedules for engagement period; Customer PM owns post-engagement
Distribution | IT Director + Customer PM + ECS PM (during engagement) | Customer to confirm distribution list post-engagement

## R&R
04 -- Scorecard Configuration — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Configure OOTB PA Scorecard | R/A | I | ECS Consultant.
Set thresholds on scorecard KPIs | R (propose) | A (approve) | ECS proposes; IT Director approves.
Schedule monthly review calendar invite | R | A | ECS PM schedules during engagement; Customer PM takes over.
Distribute monthly scorecard | N/A (during engagement: ECS) | R/A (post-engagement) | Customer IT Director distributes post-handover.

## Consultant Guide
04 -- Scorecard Configuration — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Scorecard timing
Do not publish the scorecard until at least 2 weeks of data have collected. A scorecard with 3 data points is misleading. Present the scorecard at the 30-day review meeting -- by then there is enough data to show meaningful trends.
Trend arrow language
Coach the IT Director on trend arrows: a down arrow on MTTR is good (resolving faster). A down arrow on SLA compliance is bad. The direction of good is context-dependent. Include a legend note on the scorecard: 'For MTTR: lower is better. For SLA Compliance: higher is better.'
Executive presentation use
The OOTB Scorecard is PDF-exportable. Confirm the IT Director knows how to export it. Many customers use this as a one-page insert in their monthly IT leadership report. That visibility is excellent for demonstrating the value of the ServiceNow deployment.

## Adoption vs Re-engineering
04 -- Scorecard Configuration — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want a scorecard with 25 KPIs for the CIO | 5 KPIs at go-live; expand to 10 at 90-day review based on data. | 25 KPIs without baseline data are 25 numbers without context. Five focused KPIs that the IT Director understands and can act on are more valuable than 25 that require explanation. | We start with five KPIs that connect directly to your SLAs and operations. At the 90-day review, we have real performance data and we know which additional metrics would be meaningful. Building a 25-KPI scorecard before you have baseline data means you are measuring things without knowing what good looks like. | Phase 2 -- expand scorecard after 90-day baseline established.

## ServiceNow Mapping
04 -- Scorecard Configuration — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Scorecard
pa_scorecard | PA Scorecard record -- collection of indicators formatted for review | pa_scorecard
pa_target | Threshold target per indicator -- drives green/yellow/red color | pa_target
pa_score | Individual score record per collection period | pa_score