## Instructions
02 -- Stabilization Checklist
Reporting & Stabilization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Provide the definitive go/no-go stabilization checklist covering all 18-week workstreams. Each item must be confirmed before ECS transitions from delivery to hypercare and handover.
Who fills this out | ECS PM leads. One responsible party per checklist item -- either ECS or Customer. Items marked red block handover.
Sprint window | Sprint 6 -- checklist complete by Week 12
Estimated effort | 3-4 hours with ECS PM and Customer PM
Related workbooks | All Accelerator Pack workbooks · 04 Handover & Sign-Off
Success criteria
• | All checklist items green or formally accepted as known exceptions.
• | No red items that are not acknowledged by Customer PM in writing.
• | ECS PM and Customer PM have reviewed checklist together.
• | Known exceptions documented with remediation plan and owner.

## Process Decisions
02 -- Stabilization Checklist — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What happens if a stabilization item is not complete at Sprint 6? | Item is documented as a known exception with: (1) description of gap, (2) impact, (3) remediation owner, (4) remediation deadline. |  | Known exceptions with documented plans are acceptable. Undiscovered gaps after handover are not. All gaps must be surfaced and acknowledged before sign-off.
2 | Who has final authority to declare stabilization complete? | Customer IT Director signs the stabilization sign-off. ECS PM countersigns. |  | Both parties must agree. ECS cannot declare stabilization without Customer IT Director sign-off.

## Dependencies
02 -- Stabilization Checklist — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | All sprint deliverables complete per AP workbooks | Required | ECS + Customer | Sprint 6 Wk 2 | Each AP workbook has its own UAT sign-off -- those must be complete before stabilization.

## Configuration Data
02 -- Stabilization Checklist — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Foundation & Data (Month 1)
Foundation data loaded: users, locations, departments, groups | Confirm | AP-01 Foundation Pack
Assignment rules active and tested | Confirm | AP-01
SLA schedules configured and generating SLA records | Confirm | AP-01
AD/SSO integration tested (users can log in) | Confirm | AP-03 Integration Pack
SCCM or Intune SGC syncing CIs to CMDB | Confirm | AP-03 + AP-12
2. CMDB & Discovery (Month 1-2)
CSDM service taxonomy approved and populated | Confirm | AP-10/11 CMDB Pack
Discovery running on schedule, CI count plausible | Confirm | AP-12 Discovery Pack
IRE deduplication rules tested -- no duplicate CIs | Confirm | AP-12
MID Server health green (all MID Servers up) | Confirm | AP-12
CMDB governance baseline reviewed with CMDB Admin | Confirm | AP-10/11
3. ITSM Processes (Month 2)
Incident management: creation, routing, SLA, closure tested | Confirm | AP-02 ITSM Pack
Major incident process tested with P1 scenario | Confirm | AP-02
Problem management: creation, RCA, known error process tested | Confirm | AP-02
Change management: standard, normal, emergency flows tested | Confirm | AP-02
Service request fulfillment: at least 5 catalog items tested end-to-end | Confirm | AP-CAT + AP-02
4. AI & Self-Service (Month 3)
Predictive Intelligence: all 3 models active and producing suggestions | Confirm | AP-17 PI Pack
Knowledge Base: published articles in at least 2 KBs | Confirm | AP-13 Knowledge Pack
Employee Center: live and accessible to all employees | Confirm | AP-15 EC Pack
Virtual Agent: all 6 go-live topics passing UAT | Confirm | AP-16 VA Pack
Now Assist: 3 skills active and agent-facing | Confirm | AP-18 Now Assist Pack
5. Analytics & Reporting (Month 3)
PA dashboards: 3 OOTB dashboards live and owners have access | Confirm | AP-19 PA Pack
PA data collection confirmed running (check last run) | Confirm | AP-19
OOTB reports: all report catalog items accessible to owners | Confirm | AP-20 (this pack)
Scheduled report delivery tested for at least 1 report | Confirm | AP-20
6. Handover Readiness
Customer Admin named and trained for each workstream | Confirm | AP-20 WB3
All AP workbook UAT sign-offs complete | Confirm | All AP workbooks
Known exceptions documented with remediation plans | Confirm | This workbook
Customer IT Director available for sign-off meeting | Confirm | Customer PM

## R&R
02 -- Stabilization Checklist — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Complete stabilization checklist with ECS PM | R/A | Joint completion | ECS PM leads; Customer PM confirms each item.
Document known exceptions | R/A | A (acknowledge in writing) | ECS documents; Customer PM signs acknowledgment.
Schedule stabilization sign-off meeting | R | A | ECS PM schedules; Customer IT Director attends.
Sign stabilization sign-off document | R (countersign) | A (primary sign) | Customer IT Director signs first; ECS PM countersigns.

## Consultant Guide
02 -- Stabilization Checklist — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Known exception handling
A known exception is not a failure -- it is a documented risk with a plan. Every complex engagement has 2-5 known exceptions at Sprint 6. The failure mode is undocumented exceptions that surface post-handover. Use this checklist to find them all, document them, and get Customer PM acknowledgment in writing.
Red item escalation
If a checklist item is red and the customer wants to proceed to handover anyway, get it in writing. The Customer IT Director must sign an exception acknowledgment that states: the gap, the risk, the remediation owner, and the deadline. This protects ECS and gives the customer accountability for the remediation.
Checklist meeting facilitation
Run the stabilization checklist review as a joint meeting with ECS PM and Customer PM. Go line by line. For each item, ask: 'Can you confirm this is done?' If the customer cannot confirm, mark it yellow (needs verification) or red (not done). Do not mark anything green based on assumption.

## Adoption vs Re-engineering
02 -- Stabilization Checklist — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Skip the stabilization checklist -- we trust everything is working | Stabilization checklist is mandatory before sign-off. | Undiscovered gaps surface as post-handover support requests. The checklist protects both ECS and the customer. | The stabilization checklist is the final quality gate. It takes 3-4 hours and has found real issues in every engagement -- a misconfigured SLA, a MID Server that went offline, a report that was not shared to the right role. Those issues are easy to fix before handover and expensive to fix after. We do the checklist. | Non-negotiable -- stabilization checklist is required before sign-off.

## ServiceNow Mapping
02 -- Stabilization Checklist — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Reference Tables
All workstream tables | Each checklist item references the primary ServiceNow table and AP workbook | See individual AP workbooks for table references
Incident, problem, change | Core ITSM tables -- tested in stabilization check | incident, problem, change_request
cmdb_ci | CMDB health check -- CI count, Discovery last run | cmdb_ci