## Instructions
03 -- Customer Admin Training Plan
Reporting & Stabilization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Define the training plan, schedule, and competency checklist for all Customer Administrators who will own ServiceNow workstreams post-engagement.
Who fills this out | ECS PM and Customer PM jointly plan. ECS Consultants deliver training. Customer Admins complete competency checklist.
Sprint window | Sprint 6 -- all admin training complete by Week 12
Estimated effort | Training delivery: 2-4 hours per admin (varies by workstream). Planning: 2 hours.
Related workbooks | 02 Stabilization Checklist · 04 Handover & Sign-Off
Success criteria
• | One named admin per workstream confirmed and trained.
• | Each admin has completed their competency checklist independently.
• | All admins have correct ServiceNow roles and can perform their tasks without ECS assistance.
• | Escalation path documented for each admin (who to call if stuck).

## Process Decisions
03 -- Customer Admin Training Plan — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Should training be delivered individually or in a group? | Workstream-specific training delivered individually or in small groups (2-3 admins max per session). |  | Group training with mixed workstreams reduces depth. Each admin should receive hands-on training in their specific area.
2 | Should training be recorded? | Yes -- record each training session in the ServiceNow instance (screen recording) and share the recording link with the admin. |  | Recordings are the post-engagement support safety net. An admin who is stuck 3 months after handover can replay the training session.
3 | What is the escalation path after ECS handover? | Tier 1: Customer admin self-service (documentation + recordings). Tier 2: ServiceNow Community and documentation. Tier 3: ServiceNow Support (customer must have a support contract). |  | Document the escalation path explicitly. Admins who do not know where to escalate call ECS -- which is billable T&M post-engagement.

## Dependencies
03 -- Customer Admin Training Plan — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Customer Admins named for each workstream | Required | Customer | Sprint 6 Wk 1 | Cannot schedule training without named admins.
2 | Instances stable (not in active configuration change) | Required | ECS | Sprint 6 Wk 1 | Training on an unstable instance is counterproductive.

## Configuration Data
03 -- Customer Admin Training Plan — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Admin Training Schedule
ITSM Process Admin | 2 hours -- incident, request, change, problem configuration and reporting | Customer: [Name]. ECS: [Consultant name]. Sprint 6 Wk 1.
CMDB / Discovery Admin | 3 hours -- Discovery schedule management, IRE rule review, CI governance, MID Server health | Customer: [Name]. ECS: [Consultant name]. Sprint 6 Wk 1.
Service Catalog Admin | 2 hours -- catalog item maintenance, category management, fulfillment workflow updates | Customer: [Name]. ECS: [Consultant name]. Sprint 6 Wk 1.
Knowledge Base Admin | 1.5 hours -- article lifecycle, KB structure, access control, search optimization | Customer: [Name]. ECS: [Consultant name]. Sprint 6 Wk 2.
Employee Center Admin | 1.5 hours -- portal page management, widget configuration, topic taxonomy updates | Customer: [Name]. ECS: [Consultant name]. Sprint 6 Wk 2.
Virtual Agent Admin | 2 hours -- topic management, utterance tuning, NLU analytics, Phase 2 topic builds | Customer: [Name]. ECS: [Consultant name]. Sprint 6 Wk 2.
PI / Now Assist Admin | 1.5 hours -- model monitoring, accuracy review, Now Assist skill management | Customer: [Name]. ECS: [Consultant name]. Sprint 6 Wk 2.
PA / Reporting Admin | 1.5 hours -- dashboard management, indicator thresholds, report sharing, scheduled delivery | Customer: [Name]. ECS: [Consultant name]. Sprint 6 Wk 2.
HAM / SAM Admin (if in scope) | 2 hours -- asset lifecycle, stockroom management, software reconciliation | Customer: [Name]. ECS: [Consultant name]. Sprint 6 Wk 1.
2. Competency Checklist (per admin)
Admin can navigate to their primary configuration area without ECS guidance | Pass / Fail | Assessed during training session
Admin can perform their top 3 routine tasks independently | Pass / Fail | ECS observes -- admin performs without prompting
Admin can locate relevant OOTB documentation (ServiceNow Docs, Community) | Pass / Fail | Admin demonstrates search during session
Admin has confirmed access to all required ServiceNow roles | Pass / Fail | ECS verifies roles in instance
Admin has received training recording link | Pass / Fail | ECS shares recording within 24 hours of session
3. Escalation Path
Tier 1 (self-service) | Admin review of training recording + AP workbook documentation | Available immediately post-engagement
Tier 2 (community) | ServiceNow Community (community.servicenow.com) and Now Learning | Free access with customer's ServiceNow account
Tier 3 (ServiceNow Support) | Customer opens support case via Now Support portal | Requires active ServiceNow support contract -- customer must confirm
Post-engagement ECS support | T&M engagement -- contact ECS PM to scope | Not included in 18-week engagement; billable separately

## R&R
03 -- Customer Admin Training Plan — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Name admins for each workstream | I | R/A | Customer IT Director names admins before Sprint 6 Wk 1.
Schedule and deliver admin training sessions | R/A | Attend + complete competency checklist | ECS delivers; Customer Admins participate.
Record and share training sessions | R/A | I | ECS records and shares links within 24 hours.
Verify admin roles in ServiceNow | R/A | I | ECS verifies; Customer Admin confirms access.
Complete competency checklist | R (observe) | A (perform) | Each admin must perform tasks independently.

## Consultant Guide
03 -- Customer Admin Training Plan — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Training scheduling
Book all admin training in Sprint 6 Week 1-2. Do not push training to the final week -- if an admin fails the competency checklist, there is no time to remediate. Two weeks of buffer allows a re-session if needed.
Competency pass criteria
An admin passes competency when they can perform their top 3 tasks without being prompted or corrected by ECS. 'I saw you click the wrong menu but then self-correct' is a pass. 'I had to tell you where to go' is a fail requiring another session.
Escalation path documentation
The escalation path documentation is the most important artifact for preventing post-engagement support calls from becoming T&M disputes. Be explicit: ECS is not included in the escalation path after handover. ServiceNow Support is Tier 3. Any ECS involvement post-engagement is billable. Get Customer PM acknowledgment of this in the handover sign-off.

## Adoption vs Re-engineering
03 -- Customer Admin Training Plan — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We do not have time for training in Sprint 6 | Admin training is mandatory -- schedule it in Sprint 6 Week 1, not Week 2. | Untrained admins make configuration changes that break processes. The cost of undoing a bad admin change is higher than 2 hours of training. | Admin training is how we hand over the keys. Without it, the customer owns a ServiceNow instance they cannot maintain. We have seen customers change a single SLA configuration incorrectly and break ticket routing for 200 users. Two hours of training prevents that. We schedule it in Week 1 of Sprint 6 so we have buffer if anyone needs a second session. | Non-negotiable -- admin training is required before handover sign-off.

## ServiceNow Mapping
03 -- Customer Admin Training Plan — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Admin Roles
itil | ITSM process user role -- incident, request, change, problem management | sys_user_role
cmdb_admin | CMDB admin -- CI class management, IRE rules, Discovery schedule | sys_user_role
catalog_admin | Service Catalog admin -- item, category, workflow management | sys_user_role
knowledge_admin | Knowledge Base admin -- KB structure, article lifecycle, access control | sys_user_role
pa_admin | Performance Analytics admin -- indicators, thresholds, dashboard sharing | sys_user_role
ml_admin | Predictive Intelligence admin -- model management, accuracy monitoring | sys_user_role
sn_now_assist.admin | Now Assist admin -- skill management, content filtering | sys_user_role