## Instructions
04 -- Engagement Handover & Sign-Off
Reporting & Stabilization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Define the formal handover process, sign-off documentation, and transition from ECS delivery to customer-owned operations at the close of the 18-week engagement.
Who fills this out | ECS PM prepares. Customer IT Director and Customer PM sign. ECS PM countersigns.
Sprint window | Sprint 6 -- handover complete by end of Week 12
Estimated effort | 2-3 hours for handover meeting and sign-off documentation
Related workbooks | 02 Stabilization Checklist · 03 Admin Training Plan · 05 Phase 2 Readiness
Success criteria
• | Stabilization checklist fully green (or known exceptions documented and signed).
• | All admin training complete with competency sign-offs.
• | Handover meeting held with Customer IT Director, Customer PM, and ECS PM.
• | Sign-off document executed by Customer IT Director and ECS PM.
• | Hypercare period terms confirmed (2 weeks post-sign-off).

## Process Decisions
04 -- Engagement Handover & Sign-Off — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What does formal handover mean for this engagement? | Handover means: (1) stabilization checklist complete, (2) admin training complete, (3) Customer IT Director signs the engagement completion document, (4) ECS transitions to hypercare mode (2 weeks). |  | Handover does not mean ECS disappears. Hypercare provides a 2-week buffer for post-launch issues.
2 | What is included in the 2-week hypercare period? | ECS available for: configuration corrections, SLA/routing troubleshooting, admin guidance on routine tasks. NOT included: new feature builds, new catalog items, new integrations. |  | Hypercare scope boundaries protect both ECS and the customer from scope creep.
3 | What happens to open work at handover? | All open items are documented in the known exceptions log and assigned to Customer owners with deadlines. No open ECS-owned items at handover. |  | ECS must close or formally transfer every open item before sign-off. Handover with open ECS-owned items is not a handover.

## Dependencies
04 -- Engagement Handover & Sign-Off — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Stabilization checklist complete (WB2) | Required | ECS PM | Sprint 6 Wk 2 | Cannot hand over without stabilization confirmed.
2 | All admin training complete (WB3) | Required | ECS PM | Sprint 6 Wk 2 | Cannot hand over without trained admins.
3 | Customer IT Director availability for sign-off meeting | Required | Customer PM | Sprint 6 Wk 2 | Sign-off requires IT Director presence.

## Configuration Data
04 -- Engagement Handover & Sign-Off — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Handover Meeting Agenda
Agenda Item 1: Engagement summary (15 min) | ECS PM presents what was delivered -- AP workbooks, systems live, KPI baselines set | Slide deck reference: ECS Engagement Summary presentation
Agenda Item 2: Stabilization checklist review (20 min) | Review green/yellow/red items. Discuss any known exceptions. | ECS PM leads; Customer PM confirms
Agenda Item 3: Admin training confirmation (10 min) | Confirm each admin has passed competency checklist | ECS PM presents admin training summary
Agenda Item 4: Hypercare scope and boundaries (10 min) | Confirm what is and is not covered in 2-week hypercare | ECS PM presents hypercare terms
Agenda Item 5: Phase 2 roadmap preview (10 min) | ECS PM presents Phase 2 opportunities based on engagement learnings | Reference AP-20 WB5 Phase 2 Readiness
Agenda Item 6: Sign-off (5 min) | Customer IT Director and ECS PM execute sign-off document | Physical or DocuSign signature required
2. Sign-Off Document Contents
Engagement scope summary | List of all AP workbooks delivered and accepted | ECS PM prepares
Systems live at handover | List of all ServiceNow modules active with go-live dates | ECS PM prepares
Known exceptions log | All outstanding items with owner and deadline | ECS PM + Customer PM jointly prepare
Hypercare period | Start date, end date, scope, and out-of-scope items | 2 weeks from sign-off date
Customer IT Director signature | [Customer IT Director name and date] | Required for handover to be valid
ECS PM countersignature | [ECS PM name and date] | ECS PM countersigns after Customer IT Director
3. Post-Handover Contacts
Customer primary contact post-handover | [Customer IT Director name, email, phone] | For post-engagement T&M engagement
ECS primary contact post-handover | [ECS PM name, email] | For Phase 2 scoping and T&M
ServiceNow Support | support.servicenow.com -- customer must have active support contract | Customer to confirm support contract is active

## R&R
04 -- Engagement Handover & Sign-Off — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Prepare handover meeting agenda and presentation | R/A | I | ECS PM.
Prepare sign-off document | R/A | Review | ECS PM prepares; Customer PM reviews draft.
Host handover meeting | R (host) | A (attend) | ECS PM hosts; Customer IT Director + PM attend.
Execute sign-off document | R (countersign) | A (primary sign) | Customer IT Director signs first.
Transition to hypercare mode | R/A | I | ECS PM notifies team of hypercare start date.

## Consultant Guide
04 -- Engagement Handover & Sign-Off — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Sign-off meeting tone
The handover meeting should feel like a graduation, not a checkout. Open with a summary of what was built together -- the systems live, the KPIs achieved, the admins trained. End with the Phase 2 roadmap preview. The customer should leave feeling accomplished and equipped, not abandoned.
Known exceptions handling
If there are known exceptions, present them with their remediation plans and owners. Frame it as: 'Here is what is complete, here is what has a plan.' Never present an exception without a plan. A gap with a plan is a managed risk. A gap without a plan is a failure.
Hypercare enforcement
In the first week of hypercare, you will receive requests for new features, new catalog items, and new reports. These are out of scope. Respond to every one with: 'This is a great Phase 2 item -- I will add it to the Phase 2 backlog we will review at [date].' Do not say no -- say 'Phase 2.' The Phase 2 backlog is the most valuable sales document for the next engagement.

## Adoption vs Re-engineering
04 -- Engagement Handover & Sign-Off — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We are not ready to sign off -- there are too many open items | Document all open items as known exceptions with plans. Sign off on the engagement with the exception log attached. | Waiting for zero open items before sign-off means the engagement never ends. Known exceptions with plans are the OOTB pattern for complex deployments. | No complex engagement finishes with zero open items. The question is whether each open item has a clear owner, a clear deadline, and a clear remediation plan. If yes, we sign off with the exception log attached -- both parties are on record about what is outstanding. If no, we spend the next hour making sure every item has an owner and a date. | If Customer IT Director refuses to sign with documented exceptions -- escalate to ECS Practice Lead.

## ServiceNow Mapping
04 -- Engagement Handover & Sign-Off — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Handover Reference
ServiceNow Support portal | support.servicenow.com -- customer submits support cases here | External: support.servicenow.com
ServiceNow Community | community.servicenow.com -- admin self-service resource | External: community.servicenow.com
Now Learning | nowlearning.servicenow.com -- training courses for admins | External: nowlearning.servicenow.com