## Instructions
05 -- Phase 2 Readiness Assessment
Reporting & Stabilization Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Document the Phase 2 opportunity backlog based on 18-week engagement learnings, deferred items, and new capabilities identified during delivery. Provides the foundation for the next ECS engagement proposal.
Who fills this out | ECS PM compiles based on deferred items logged across all AP workbooks. Customer PM reviews and prioritizes.
Sprint window | Sprint 6 -- Phase 2 assessment presented at handover meeting
Estimated effort | 2-3 hours to compile deferred items from all AP workbooks
Related workbooks | All AP workbooks (Adoption vs. Re-engineering tabs) · 04 Handover & Sign-Off
Success criteria
• | All deferred items from AP workbooks compiled into Phase 2 backlog.
• | Phase 2 items prioritized by customer value (High/Medium/Low).
• | Indicative effort estimate provided for top 5 Phase 2 items.
• | Customer PM has reviewed and ranked Phase 2 priorities.
• | Phase 2 backlog shared with customer as a leave-behind document.

## Process Decisions
05 -- Phase 2 Readiness Assessment — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | How should Phase 2 items be prioritized? | Business value to the customer (High/Medium/Low). High = operational pain point or significant efficiency gain. Medium = nice to have. Low = theoretical benefit. |  | Customer-facing prioritization drives the next engagement scope. ECS should not unilaterally rank Phase 2 items -- the customer prioritizes based on their operational needs.
2 | Should Phase 2 include items not on the original blueprint? | Yes -- capture any new requirements that emerged during the 18-week engagement. |  | Delivery always surfaces requirements that were not in the original scope. These are the highest-value Phase 2 items because they are based on real operational experience, not pre-engagement assumptions.
3 | Should ECS provide a proposal for Phase 2 at the handover meeting? | No -- provide the Phase 2 backlog and indicative estimates only. Formal proposal is a separate sales activity. |  | Mixing delivery handover with sales creates awkwardness and potential conflict of interest. The backlog is a gift to the customer; the proposal comes separately.

## Dependencies
05 -- Phase 2 Readiness Assessment — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | All AP workbook Adoption vs. Re-engineering tabs reviewed | Required | ECS PM | Sprint 6 Wk 2 | Every deferred item from every AP workbook is a Phase 2 candidate.

## Configuration Data
05 -- Phase 2 Readiness Assessment — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Phase 2 Backlog -- AI & Self-Service
VA: Teams/Slack channel integration | High | 2-3 sprints. Requires Azure AD app registration and bot configuration.
VA: Topic library expansion (7-15 additional topics) | High | 1-2 sprints per 5 topics. Data-driven from unhandled intent report.
PI: Agent-level Assignment Intelligence | Medium | 1 sprint. Requires 6+ months of group-level accuracy baseline.
PI: Predictive Fields (custom field prediction) | Medium | 1-2 sprints. Each custom field is a separate ML Solution.
Now Assist: GenAI for Change (change assessment) | Medium | 1 sprint. Requires mature Change Management process.
Now Assist: AI Search corpus expansion (SharePoint connector) | High | 2-3 sprints. Requires SharePoint Online connector and content governance.
Now Assist: Auto-generation mode (all skills) | Low | 1 sprint. Enable after 90-day on-demand baseline proven.
2. Phase 2 Backlog -- ITSM & Platform
ITSM: CSM (Customer Service Management) for external-facing requests | Medium | 4-6 sprints. Significant scope -- separate engagement.
Catalog: Additional catalog items (beyond go-live set) | High | 0.5 sprint per 10 items. Customer-driven -- use unmet request data.
Integration: ACD handoff for VA (Genesys/Five9) | Low | 3-4 sprints. Requires ACD vendor engagement and middleware.
CMDB: Cloud CIs via AWS/Azure SGC | High | 1-2 sprints. OOTB SGC connectors -- high value if cloud-heavy environment.
Event Management: Alert consolidation and correlation | Medium | 3-4 sprints. Was descoped from 18-week engagement.
3. Phase 2 Backlog -- Analytics & Reporting
PA: Custom indicator library (FCR by team, SLA by category) | High | 1-2 sprints. Builds on 6-month OOTB baseline.
PA: Department-level dashboards (HR, Finance, Facilities) | Medium | 1 sprint per department. Requires ITSM usage data per department.
PA: AI-assisted forecasting with Now Assist | Low | 2-3 sprints. Requires 12+ months of PA trend data.
Reporting: SharePoint / Power BI integration | Medium | 2-3 sprints. Requires Power BI connector and data governance review.
4. Phase 2 Effort Estimates (Top 5 by Customer Priority)
Priority 1 (Customer to complete) | [Item name] | [Indicative sprints]
Priority 2 (Customer to complete) | [Item name] | [Indicative sprints]
Priority 3 (Customer to complete) | [Item name] | [Indicative sprints]
Priority 4 (Customer to complete) | [Item name] | [Indicative sprints]
Priority 5 (Customer to complete) | [Item name] | [Indicative sprints]

## R&R
05 -- Phase 2 Readiness Assessment — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Compile deferred items from all AP workbooks | R/A | I | ECS PM compiles Phase 2 backlog.
Add new requirements surfaced during delivery | R/A | I | ECS Consultants contribute workstream-specific items.
Prioritize Phase 2 backlog (High/Medium/Low) | I (facilitate) | R/A (decide) | Customer PM prioritizes with ECS PM facilitation.
Present Phase 2 backlog at handover meeting | R/A | Receive | ECS PM presents; Customer PM takes as leave-behind.
Formal Phase 2 proposal | N/A (separate sales activity) | N/A | Formal proposal is separate from handover -- do not conflate.

## Consultant Guide
05 -- Phase 2 Readiness Assessment — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Phase 2 backlog as sales asset
The Phase 2 backlog is the most valuable sales document that comes out of an 18-week engagement. It is grounded in real experience with the customer's environment, real operational pain points, and real deferred requirements. Every item on the backlog is a justified opportunity. Share it generously -- the customer views it as a roadmap, ECS views it as a pipeline.
Prioritization facilitation
When facilitating Phase 2 prioritization, ask: 'Which of these items, if delivered, would most improve your team's daily operations?' This is more productive than asking 'which do you want most' -- operational pain drives honest prioritization. The IT Director's top priority is almost always different from the Service Desk Manager's. Capture both perspectives.
Indicative estimates
Indicative estimates are ranges, not commitments. 'This is a 2-3 sprint item' gives the customer enough to budget-plan without creating a contractual obligation. Always include the caveat: 'These estimates assume an OOTB-first approach. Custom development would add scope.'

## Adoption vs Re-engineering
05 -- Phase 2 Readiness Assessment — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want to start Phase 2 immediately -- skip the stabilization period | 2-week stabilization period is required before Phase 2 begins. | Starting Phase 2 configuration before the go-live platform stabilizes introduces dependency risks and makes defect isolation nearly impossible. | The 2-week stabilization period is when we watch the live data and confirm everything is working as designed. Starting Phase 2 during this window means we might be building on top of a misconfiguration that has not surfaced yet. Two weeks is a small investment to ensure Phase 2 is built on a solid foundation. | Phase 2 begins after 2-week stabilization hypercare period closes.

## ServiceNow Mapping
05 -- Phase 2 Readiness Assessment — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Phase 2 Reference
All AP workbook Adoption vs. Re-engineering tabs | Source of all deferred items -- compile from each workbook | See individual AP workbooks
ServiceNow Product Roadmap | docs.servicenow.com -- future OOTB capabilities to include in Phase 2 planning | External: docs.servicenow.com