## Instructions
01 — VA Scope & Channel Decisions
Virtual Agent Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Establish which channels, languages, and business domains the OOTB Now Assist Virtual Agent will serve at go-live. Decisions here gate topic design (WB2) and handoff configuration (WB3).
Who fills this out | ECS Consultant completes Tabs 2, 4, 6, 7, 8. Customer Product Owner + IT Lead complete Tab 2 process decisions and Tab 4 yellow cells.
Sprint window | Sprint 5 — complete by end of Week 10
Estimated effort | 2-3 hours with Customer PM and IT Lead
Related workbooks | 02 Topic Design & NLU Intent Library · 03 Handoff & Escalation · AP-15 Employee Center · AP-13 Knowledge Management
Success criteria
• | Primary channel confirmed (portal, Teams, Slack).
• | Business domains in scope agreed (IT, HR, other).
• | Language support decision made.
• | Live-agent handoff requirement confirmed.
• | Customer VA Admin named and engaged.

## Process Decisions
01 — VA Scope & Channel Decisions — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | Which channel should Virtual Agent launch on first? | Employee Center portal (web) — Teams/Slack deferred to Phase 2. |  | Teams adds OAuth app registration complexity. The portal widget is zero-dependency and immediately available once Employee Center is live (AP-15).
2 | Which business domains should VA cover at go-live? | IT (incidents, requests, password reset) + HR FAQ (read-only knowledge deflection) only. |  | Limiting to 2 domains keeps the topic set manageable in a 2-sprint window. HR FAQ is read-only — no fulfillment workflow, just KB deflection.
3 | Should VA support multiple languages? | English only at go-live. Multi-language is Phase 2. |  | Each additional locale requires separate NLU training utterances. Deferring ensures go-live quality in English is high before expanding.
4 | Is live-agent handoff required? | Yes — OOTB Connect Chat → Agent Workspace (IT Tier 1 queue). |  | OOTB native handoff. No third-party ACD (Genesys, Five9) integration in the 18-week scope.
5 | Who owns VA topic maintenance post-go-live? | Customer VA Admin (trained by ECS in Sprint 6). |  | ECS trains 1-2 customer admins during Sprint 6. Customer owns utterance tuning and new topic builds post-stabilization.

## Dependencies
01 — VA Scope & Channel Decisions — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Employee Center published (AP-15) | Required | ECS + Customer | Sprint 5 Wk 1 | VA widget is embedded in EC — EC must be live before VA can be launched.
2 | Knowledge Base published (AP-13) | Required | ECS + Customer | Sprint 5 Wk 1 | HR FAQ and IT KB topics require published articles to deflect to.
3 | Service Catalog items published (AP-CAT) | Required | ECS + Customer | Sprint 5 Wk 1 | VA fulfillment topics (password reset, equipment request) link to published catalog items.
4 | Now Assist for ITSM license confirmed | Required | Customer | Before Sprint 5 | Customer must confirm Now Assist entitlement before topic build begins.
5 | Agent Workspace queue configured | Required | ECS | Sprint 5 Wk 1 | Live-agent handoff requires at least one active IT queue in Agent Workspace.

## Configuration Data
01 — VA Scope & Channel Decisions — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Channel & Access
Primary channel | Employee Center portal embedded widget | OOTB CSM Portal widget — no custom CSS
Secondary channel | Microsoft Teams (Phase 2 only) | Defer until portal containment baseline is established
Authentication | Authenticated users only — no anonymous access | VA personalizes greetings and prefills user context from sys_user
Widget placement | Bottom-right persistent launcher (OOTB default) | Do not move or restyle the launcher widget
2. Conversation Settings
Greeting message | Hi, I'm your IT Help Assistant. How can I help you today? | Customer to approve exact wording
Fallback message | I'm not sure how to help with that. Let me connect you to a live agent. | Triggers on 2 consecutive unrecognized intents
Session timeout (minutes) | 15 | OOTB default — do not reduce below 10
Max unresolved turns before handoff offer | 3 | After 3 unresolved turns VA proactively offers live agent
3. Scope
Business domains | IT Service Management + HR (read-only FAQ) | Limit entitlement to ITSM + HR domains
Go-live topic count (max) | 15 | Recommend 6-topic MVP; 15 is the ceiling for a 2-sprint window
Language | English only | Multi-language deferred to Phase 2

## R&R
01 — VA Scope & Channel Decisions — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Confirm Now Assist license entitlement | I | R/A | Customer IT Director.
Define in-scope VA topics and channels | R/A | I | ECS Architect.
Approve go-live channel and domain scope | I | R/A | Customer PM sign-off.
Name and engage Customer VA Admin | I | R/A | Customer to identify admin before Sprint 5.
Configure VA widget in Employee Center | R/A | I | ECS configures; Customer UATs.

## Consultant Guide
01 — VA Scope & Channel Decisions — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Channel defer rationale
If the customer pushes for Teams on Day 1: Teams requires an Azure AD app registration, bot channel configuration in Azure, and VA bot configuration in ServiceNow. This is a 2-3 day setup. Portal widget is zero-dependency and delivers the identical NLU experience. Establish baseline, then expand.
Domain limit rationale
Two domains (IT + HR FAQ) is the ceiling for Sprint 5 topic build. Each additional domain adds fulfillment complexity. HR FAQ is deliberately read-only — no HR record creates or approvals in scope.
VA Admin engagement
The Customer VA Admin must be identified before Sprint 5 starts. They will add utterances during UAT, own the weekly unhandled intent review post-go-live, and build Phase 2 topics. Without this person named, the go-live is at risk.

## Adoption vs Re-engineering
01 — VA Scope & Channel Decisions — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
We want Teams and Slack on Day 1 | Start with portal; add Teams/Slack in Phase 2 after baseline. | Portal widget delivers identical NLU experience with zero additional configuration. Multi-channel at launch doubles setup scope. | The portal widget and Teams bot use the same NLU engine and the same topics. Starting with portal lets us go live faster and prove containment before adding channels. We'll build Teams in Phase 2 with real adoption data to guide it. | When portal containment exceeds 20% and customer has Azure AD bot registration resources available.
We need to cover all 10 of our business domains | 2 domains (IT + HR FAQ) at go-live; phase additional domains quarterly. | Each domain adds topic build, utterance training, UAT, and handoff configuration. 10 domains in 2 sprints is not achievable at acceptable quality. | We want every domain to work well, not have 10 domains working poorly. The OOTB pattern is to launch with the highest-volume use cases, prove the model, then expand. Your top 2 domains will cover the majority of your employees' needs. | Never — always phase by domain, even post-go-live.

## ServiceNow Mapping
01 — VA Scope & Channel Decisions — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Now Assist Virtual Agent Studio
Topic designer | OOTB topic builder — conversation flows, panels, NLU intents | va_topic_block, va_panel_choice, va_panel_text
NLU Workbench | Intent training interface — utterances stored per intent | ml_intent, ml_solution
VA Analytics Dashboard | Containment rate, handoff rate, top topics, unhandled intents | sn_va_analytics, va_conversation_log
2. Channel & Handoff
Employee Center widget | Embedded launcher — OOTB, placed via EC page editor | sp_widget (VA launcher sys_id)
Connect Chat | Real-time handoff bridge from VA to Agent Workspace | chat_message, chat_session, chat_queue
Agent Workspace | Live-agent handoff destination — OOTB queue routing | awa_session, chat_queue