## Instructions
03 — Live-Agent Handoff & Escalation Configuration
Virtual Agent Accelerator Pack · ECS Federal · ServiceNow Practice
Purpose | Configure the OOTB Connect Chat handoff from Virtual Agent to Agent Workspace. Covers trigger conditions, queue routing, context transfer, and after-hours handling.
Who fills this out | ECS Consultant configures. Customer IT Lead validates queue names and confirms agent availability during UAT.
Sprint window | Sprint 5 — handoff configured and tested alongside VA topic UAT
Estimated effort | 4-6 hours including Agent Workspace queue setup and UAT
Related workbooks | 01 VA Scope & Channel Decisions · 02 Topic Design & NLU Intent Library
Success criteria
• | Live-agent handoff triggers correctly from all 3 escalation conditions.
• | Conversation transcript transfers to agent on handoff.
• | After-hours message displays correctly when queue is closed.
• | At least 2 agents tested in Agent Workspace to receive VA handoffs.
• | Queue wait time display confirmed in portal.

## Process Decisions
03 — Live-Agent Handoff & Escalation Configuration — Process Decisions
Decisions to make collectively. ECS recommendation pre-filled.
# | Decision | ECS Recommendation (OOTB) | Customer Decision | Rationale / Notes
1 | What should trigger a live-agent handoff? | Three triggers: (1) explicit user request, (2) 2 consecutive unrecognized intents, (3) 3 clarification retries exhausted. |  | OOTB Now Assist supports all three trigger types natively. Single-trigger (explicit only) misses users who are frustrated but do not ask for a person.
2 | Which Agent Workspace queue should VA route to? | Single IT Tier 1 Support queue for all topics in the 18-week scope. |  | Multi-queue routing by topic adds configuration complexity. Single queue is the OOTB pattern for initial deployment. Topic-based routing is Phase 2.
3 | What context should be transferred to the agent? | Last 5 VA conversation turns + user identity (name, email, dept) + open incident numbers (last 3). |  | OOTB Connect Chat passes conversation transcript as a prepended message. User identity is pulled from sys_user automatically.
4 | How should after-hours requests be handled? | Display business hours message + create an incident for next-day follow-up. Do not route to voicemail or email callback. |  | Incident creation is the OOTB after-hours pattern. Voicemail and email callback require integrations outside the 18-week scope.
5 | Should queue wait time be displayed? | Yes — OOTB Agent Workspace queue position estimate displayed in portal. |  | Transparent wait time reduces user frustration and repeat handoff requests.

## Dependencies
03 — Live-Agent Handoff & Escalation Configuration — Dependencies
Other Packs and source data that must be in place before configuration.
# | Dependency | Status | Owner | Due | Notes
1 | Agent Workspace enabled | Required | ECS | Sprint 5 Wk 1 | Must be enabled and at least one IT queue configured before VA handoff can be tested.
2 | At least 2 agents available for UAT | Required | Customer | Sprint 5 UAT week | At least 2 agents must be set to Available in Agent Workspace during UAT testing.
3 | Business hours schedule | Required | Customer | Sprint 5 Wk 1 | Customer must provide business hours (e.g. M-F 8am-5pm) and timezone for after-hours message config.
4 | VA handoff panel added to each topic | Required | ECS | Sprint 5 Wk 2 | Every topic's conversation flow must include a terminal handoff panel as the escalation path.

## Configuration Data
03 — Live-Agent Handoff & Escalation Configuration — Configuration Data
Final OOTB-aligned configuration. Yellow-shaded values are customer-confirmed inputs.
Field / Setting | Value | Notes
1. Handoff Configuration
Handoff mechanism | OOTB Connect Chat — Live Agent Handoff panel in Now Assist Studio | Native VA panel — no scripting required
Target queue | IT Tier 1 Support | Customer to confirm exact queue name from Agent Workspace
Trigger 1 — explicit request | User says 'talk to a person', 'live agent', 'human', etc. | OOTB NLU engine recognizes handoff intent natively
Trigger 2 — unrecognized intents | 2 consecutive unrecognized intents → auto-escalation | Prevents frustration loops before user must ask explicitly
Trigger 3 — clarification exhausted | 3 clarification retries → proactive handoff offer | Topic-level escalation after clarification loop fails
2. Context Transfer
Conversation turns transferred | 5 (last 5 turns) | Sent as prepended message to agent in Connect Chat
User identity transferred | Name, email, department, open incidents (last 3) | Pulled from sys_user and incident table automatically
Agent briefing instruction | Agents must read the first Connect Chat message (VA transcript) before greeting the user | Coach agents during handoff training session
3. After-Hours & Queue
Business hours | [Customer: e.g. Monday-Friday, 8:00am-5:00pm Central] | Customer to confirm hours and timezone
After-hours message | Our team is available Monday-Friday, 8am-5pm [timezone]. I've created an incident — someone will follow up with you next business day. | Customer to approve wording and confirm timezone
Queue wait time display | Enabled — OOTB queue position estimate shown in portal | Agent Workspace exposes queue depth OOTB
Handoff confirmation message | Connecting you now. An agent will be with you shortly. | Customer to approve wording

## R&R
03 — Live-Agent Handoff & Escalation Configuration — Roles & Responsibilities
RACI: R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | ECS | Customer | Notes
Configure Agent Workspace queue | R/A | Provide queue name + agent assignments | ECS configures; Customer confirms queue membership.
Add handoff panels to all VA topics | R/A | I | ECS adds; Customer reviews in Studio.
Configure after-hours schedule | R/A | Provide business hours details | Customer confirms hours; ECS configures cmn_schedule.
UAT — trigger all 3 handoff conditions | R | A | ECS leads; Customer agent performs receipt test.
UAT — validate transcript transfer to agent | R | A | Both parties confirm transcript appears in agent session.
Train agents on receiving VA handoffs | R (overview) | A (ongoing) | ECS delivers 30-min agent briefing in Sprint 6.

## Consultant Guide
03 — Live-Agent Handoff & Escalation Configuration — Consultant Implementation Guide
Internal reference for the ECS Solution Architect / Process Consultant.
Single queue discipline
For the 18-week scope, route all VA handoffs to one IT Tier 1 queue. Multi-queue routing by topic adds configuration scope and routing logic that is not warranted in Sprint 5. Log topic-based routing as a Phase 2 item if the customer raises it.
After-hours test method
Test after-hours handling by temporarily changing the business hours schedule (cmn_schedule) to a closed window. Confirm the after-hours message displays in portal. Revert the schedule immediately after testing.
Transcript format coaching
The OOTB transcript appears as the first message in the agent's Connect Chat session, prepended automatically. Coach agents: 'The first message in every VA transfer is the conversation history — read it before saying hello.' This prevents agents from asking users to repeat what they already told the bot.
ACD integration pushback
If the customer has Genesys, Five9, or another ACD and insists on routing there: this is a post-go-live integration project. It requires middleware, custom event payloads, and ACD-side bot routing configuration. None of this is OOTB and none is in 18-week scope. Log as Phase 2.

## Adoption vs Re-engineering
03 — Live-Agent Handoff & Escalation Configuration — Adoption vs Re-engineering
When the customer says 'but our old tool did X.' Use this language.
Customer Request / Legacy Pattern | OOTB Pattern | Why OOTB Wins | Suggested Pushback Language | When to Customize Anyway
Route handoffs to our existing ACD (Genesys / Five9) | OOTB Connect Chat → Agent Workspace is the certified handoff target. | Third-party ACD integration requires middleware, custom event payloads, and license coordination — not OOTB and not achievable in 18-week sprint. | Agent Workspace is ServiceNow's certified real-time chat handoff platform. ACD integration is a Phase 2 project we can scope once go-live is stable. Your agents use Agent Workspace for all ServiceNow work anyway — the VA handoff lands in the same place. | Post-go-live Phase 2 project with dedicated integration sprint.
Different queues per topic | Single IT Tier 1 queue at go-live; topic-based routing in Phase 2. | Multi-queue routing in Sprint 5 doubles handoff configuration scope. Single-queue is the OOTB-aligned initial deployment pattern. | One queue at go-live means every handoff lands where your best agents are. Topic-based routing is a Phase 2 enhancement — once we know which topics generate the most handoffs, we can route them intelligently. Guessing now adds complexity without data. | Phase 2 — after 90 days of handoff volume data.

## ServiceNow Mapping
03 — Live-Agent Handoff & Escalation Configuration — ServiceNow Mapping
Internal reference — target tables, OOTB features used, integrations.
1. Connect Chat & Agent Workspace
Connect Chat session | Real-time messaging bridge — VA to agent | chat_session, chat_message
Chat queue | Agent Workspace queue — receives VA handoffs | chat_queue
AWA session | Agent Workspace live-agent session record | awa_session
VA handoff panel | OOTB Now Assist Studio panel — drops into Connect Chat | va_panel_live_agent
2. Scheduling & After-Hours
Business hours schedule | OOTB cmn_schedule used for after-hours logic in VA flow | cmn_schedule, cmn_schedule_span
After-hours incident creation | OOTB incident record producer triggered by after-hours VA flow | incident